## Roadmap
quarter | theme | features | successMetrics
Q1 | MVP foundation | Auth, onboarding, language, farm, cows, calves, records, reminders, base dashboard | First 50 pilot farms onboarded; daily milk record flow stable
Q2 | Accounting and OCR | Manual accounting, settlement, OCR slips, reports, notifications | 80% pilot farms use accounting; OCR review save success > 90%
Q3 | AI and engagement | AI assistant, goals, profile stats, support, achievements, leaderboard | AI usage by 40% active farms; retention improved
Q4 | Admin, scale and commercialization | Admin monitoring, subscriptions, analytics, performance, security hardening, go-live | Paid conversion, stable production operations, support SLA met

## MVP MoSCoW
Category | Scope
Must Have | Authentication, language, farm setup, cow/calf management, milk records, reminders, accounting basics, reports, settings, admin basics, security/RLS
Should Have | OCR slip scanning, settlement processing, notifications, AI assistant, export, profile statistics
Could Have | Achievements, leaderboard, support center, advanced analytics, shareable cards
Won't Have for MVP | WhatsApp/SMS automation, full ERP integrations, marketplace, advanced IoT integrations

## KPIs
KPI | Target
North Star | Weekly Active Farms with meaningful farm operation
Daily active farms | Increase month over month
Milk records | 80% active farms record milk 5 days/week
OCR adoption | 50% accounting users scan at least one slip/month
AI usage | 40% active farms ask at least one AI question/month
Retention | 60%+ 30-day retention