## Releases
releaseId | theme | featuresIncluded | storyCount | storyPoints | dependencies | risks | acceptanceCriteria
Release 1 | MVP farm operations | Authentication & Onboarding, Calf Management, Cow Management, Farm & Member Management, Records Management, Reminder Engine, Settings & Personalization | 181 | 637 | Prior release foundation and successful QA gates. | Scope creep, financial accuracy, provider setup, localization gaps and performance. | All Must stories complete, no Critical/High defects, release checklist approved.
Release 2 | Financial automation and reporting | AI Slip Scanning & OCR, Accounting & Settlement, Notifications, Reports & Analytics | 105 | 468 | Prior release foundation and successful QA gates. | Scope creep, financial accuracy, provider setup, localization gaps and performance. | All Must stories complete, no Critical/High defects, release checklist approved.
Release 3 | Engagement, AI and support | Achievements & Leaderboard, Dugdhmitra AI Assistant, Profile & Statistics, Support Center | 73 | 269 | Prior release foundation and successful QA gates. | Scope creep, financial accuracy, provider setup, localization gaps and performance. | All Must stories complete, no Critical/High defects, release checklist approved.
Release 4 | Admin, scale, hardening and go-live | Admin Panel, Home Dashboard, Quality, Security & Performance, Settings & Personalization | 142 | 648 | Prior release foundation and successful QA gates. | Scope creep, financial accuracy, provider setup, localization gaps and performance. | All Must stories complete, no Critical/High defects, release checklist approved.