## Risks
riskId | risk | category | probability | impact | description | mitigation | owner | status
RISK-001 | Financial calculation mismatch | Technical/Business | Medium | Critical | Settlement/profit errors reduce trust. | Automated reconciliation, source-of-truth rules, UAT with real slips. | Product/Tech Lead | Open
RISK-002 | OCR accuracy below expectation | AI/OCR | High | High | Farmers need repeated rescans. | Native camera, validation, fallback, manual review, image guidance. | Product/Tech Lead | Open
RISK-003 | Cross-farm data leak | Security | Low | Critical | Privacy breach. | RLS tests, admin audit, penetration testing. | Product/Tech Lead | Open
RISK-004 | iOS PWA storage/session issues | Technical | Medium | High | iPhone users cannot navigate reliably. | iOS-specific QA and session fallback. | Product/Tech Lead | Open
RISK-005 | Localization gaps | Product | Medium | Medium | Mixed language reduces usability. | i18n audit and screenshot QA. | Product/Tech Lead | Open
RISK-006 | Provider cost spike | AI/OCR | Medium | Medium | OpenAI/OCR usage grows unexpectedly. | Quotas, compression, cache, usage dashboards. | Product/Tech Lead | Open
RISK-007 | Slow dashboard at scale | Performance | Medium | High | Poor first impression. | Materialized views, caching and load tests. | Product/Tech Lead | Open
RISK-008 | Reminder lifecycle bugs | Functional | Medium | High | Wrong animal care reminders. | Trigger tests and regression pack. | Product/Tech Lead | Open
RISK-009 | Push notifications unreliable | Integration | Medium | Medium | Users miss important alerts. | In-app fallback, retry and device diagnostics. | Product/Tech Lead | Open
RISK-010 | Scope creep | Project | High | High | Timeline slips. | MoSCoW control, change request process. | Product/Tech Lead | Open
RISK-011 | Admin protected action misuse | Security | Low | High | Farm suspension/delete mistakes. | Confirmation, audit, role limits, protected delete. | Product/Tech Lead | Open
RISK-012 | Database migration failure | Technical | Medium | Critical | Data loss or downtime. | Staging rehearsal, backup, rollback and compatibility views. | Product/Tech Lead | Open

## Matrix
Probability | Impact | Action
High | Critical | Escalate immediately and create mitigation sprint item
Medium | High | Track weekly and assign owner
Low | High | Monitor and validate controls
Medium | Medium | Mitigate through backlog and QA