## Sprints
sprint | length | objectives | epics | storyIds | storyCount | storyPoints | dependencies | definitionOfDone
Sprint 1 | 2 weeks | Authentication, language selection, onboarding | EPIC-AUTH, EPIC-SET | US-AUTH-001, US-AUTH-002, US-AUTH-002A, US-AUTH-003, US-AUTH-004, US-AUTH-004A, US-AUTH-005, US-AUTH-006, US-AUTH-006A, US-AUTH-007, US-AUTH-008, US-AUTH-008A, US-AUTH-009, US-AUTH-010, US-AUTH-010A, US-AUTH-011, US-AUTH-012, US-AUTH-012A, US-AUTH-013, US-AUTH-014, US-AUTH-014A, US-AUTH-015, US-AUTH-016, US-AUTH-016A, US-AUTH-017, US-AUTH-018, US-AUTH-018A, US-AUTH-019, US-AUTH-020, US-AUTH-020A, US-SET-001, US-SET-002, US-SET-002A, US-SET-003, US-SET-004, US-SET-004A, US-SET-005, US-SET-006, US-SET-006A, US-SET-007 | 54 | 206 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 2 | 2 weeks | Farm management and cow management | EPIC-FARM, EPIC-COW | US-FARM-001, US-FARM-002, US-FARM-002A, US-FARM-003, US-FARM-004, US-FARM-004A, US-FARM-005, US-FARM-006, US-FARM-006A, US-FARM-007, US-FARM-008, US-FARM-008A, US-FARM-009, US-FARM-010, US-FARM-010A, US-FARM-011, US-FARM-012, US-FARM-012A, US-FARM-013, US-FARM-014, US-FARM-014A, US-FARM-015, US-FARM-016, US-FARM-016A, US-COW-001, US-COW-002, US-COW-002A, US-COW-003, US-COW-004, US-COW-004A, US-COW-005, US-COW-006, US-COW-006A, US-COW-007, US-COW-008, US-COW-008A, US-COW-009, US-COW-010, US-COW-010A, US-COW-011 | 51 | 178 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 3 | 2 weeks | Calf management and milk records | EPIC-CALF, EPIC-REC | US-CALF-001, US-CALF-002, US-CALF-002A, US-CALF-003, US-CALF-004, US-CALF-004A, US-CALF-005, US-CALF-006, US-CALF-006A, US-CALF-007, US-CALF-008, US-CALF-008A, US-CALF-009, US-CALF-010, US-CALF-010A, US-CALF-011, US-CALF-012, US-CALF-012A, US-CALF-013, US-CALF-014, US-CALF-014A, US-CALF-015, US-REC-001, US-REC-002, US-REC-002A, US-REC-003, US-REC-004, US-REC-004A, US-REC-005, US-REC-006, US-REC-006A, US-REC-007, US-REC-008, US-REC-008A, US-REC-009, US-REC-010, US-REC-010A, US-REC-011, US-REC-012, US-REC-012A | 49 | 166 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 4 | 2 weeks | Reminders and vaccinations | EPIC-REM, EPIC-REC, EPIC-NOTIF | US-REM-001, US-REM-002, US-REM-002A, US-REM-003, US-REM-004, US-REM-004A, US-REM-005, US-REM-006, US-REM-006A, US-REM-007, US-REM-008, US-REM-008A, US-REM-009, US-REM-010, US-REM-010A, US-REM-011, US-REM-012, US-REM-012A, US-REM-013, US-REM-014, US-REM-014A, US-REM-015, US-REM-016, US-REM-016A, US-REM-017, US-REM-018, US-REM-018A, US-NOTIF-001, US-NOTIF-002, US-NOTIF-002A, US-NOTIF-003, US-NOTIF-004, US-NOTIF-004A, US-NOTIF-005, US-NOTIF-006, US-NOTIF-006A, US-NOTIF-007, US-NOTIF-008, US-NOTIF-008A, US-NOTIF-009 | 51 | 197 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 5 | 2 weeks | Accounting and settlements | EPIC-ACC | US-ACC-001, US-ACC-002, US-ACC-002A, US-ACC-003, US-ACC-004, US-ACC-004A, US-ACC-005, US-ACC-006, US-ACC-006A, US-ACC-007, US-ACC-008, US-ACC-008A, US-ACC-009, US-ACC-010, US-ACC-010A, US-ACC-011, US-ACC-012, US-ACC-012A, US-ACC-013, US-ACC-014, US-ACC-014A, US-ACC-015, US-ACC-016, US-ACC-016A, US-ACC-017, US-ACC-018, US-ACC-018A | 27 | 124 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 6 | 2 weeks | OCR and AI assistant | EPIC-OCR, EPIC-AI | US-OCR-001, US-OCR-002, US-OCR-002A, US-OCR-003, US-OCR-004, US-OCR-004A, US-OCR-005, US-OCR-006, US-OCR-006A, US-OCR-007, US-OCR-008, US-OCR-008A, US-OCR-009, US-OCR-010, US-OCR-010A, US-OCR-011, US-OCR-012, US-OCR-012A, US-OCR-013, US-OCR-014, US-OCR-014A, US-OCR-015, US-OCR-016, US-OCR-016A, US-OCR-017, US-OCR-018, US-OCR-018A, US-AI-001, US-AI-002, US-AI-002A, US-AI-003, US-AI-004, US-AI-004A, US-AI-005, US-AI-006, US-AI-006A, US-AI-007, US-AI-008, US-AI-008A, US-AI-009 | 54 | 215 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 7 | 2 weeks | Reports and notifications | EPIC-REP, EPIC-NOTIF | US-REP-001, US-REP-002, US-REP-002A, US-REP-003, US-REP-004, US-REP-004A, US-REP-005, US-REP-006, US-REP-006A, US-REP-007, US-REP-008, US-REP-008A, US-REP-009, US-REP-010, US-REP-010A, US-REP-011, US-REP-012, US-REP-012A, US-REP-013, US-REP-014, US-REP-014A, US-REP-015, US-REP-016, US-REP-016A, US-REP-017, US-REP-018, US-REP-018A | 27 | 119 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 8 | 2 weeks | Admin panel and support | EPIC-ADMIN, EPIC-SUP | US-SUP-001, US-SUP-002, US-SUP-003, US-SUP-004, US-SUP-005, US-SUP-006, US-SUP-007, US-SUP-008, US-SUP-009, US-SUP-010, US-SUP-011, US-SUP-012, US-SUP-013, US-SUP-014, US-ADMIN-001, US-ADMIN-002, US-ADMIN-003, US-ADMIN-004, US-ADMIN-005, US-ADMIN-006, US-ADMIN-007, US-ADMIN-008, US-ADMIN-009, US-ADMIN-010, US-ADMIN-011, US-ADMIN-012, US-ADMIN-013, US-ADMIN-014, US-ADMIN-015, US-ADMIN-016, US-ADMIN-017 | 31 | 132 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 9 | 2 weeks | Performance, security, bug fixes | EPIC-QA, EPIC-ACH | US-ACH-001, US-ACH-002, US-ACH-003, US-ACH-004, US-ACH-005, US-ACH-006, US-ACH-007, US-ACH-008, US-ACH-009, US-ACH-010, US-ACH-011, US-ACH-012, US-ACH-013, US-ACH-014, US-ACH-015, US-QA-001, US-QA-002, US-QA-003, US-QA-004, US-QA-005, US-QA-006, US-QA-007, US-QA-008, US-QA-009, US-QA-010, US-QA-011, US-QA-012, US-QA-013, US-QA-014, US-QA-015, US-X-001, US-X-002, US-X-003, US-X-004, US-X-005, US-X-006, US-X-007, US-X-008, US-X-009, US-X-010 | 80 | 375 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.
Sprint 10 | 2 weeks | UAT and release preparation | EPIC-QA | US-DASH-001, US-DASH-002, US-DASH-002A, US-DASH-003, US-DASH-004, US-DASH-004A, US-DASH-005, US-DASH-006, US-DASH-006A, US-DASH-007, US-DASH-008, US-DASH-008A, US-DASH-009, US-DASH-010, US-DASH-010A, US-DASH-011, US-DASH-012, US-DASH-012A, US-DASH-013, US-DASH-014, US-DASH-014A, US-DASH-015, US-DASH-016, US-DASH-016A, US-DASH-017, US-DASH-018, US-DASH-018A, US-DASH-019, US-DASH-020, US-DASH-020A, US-PROF-001, US-PROF-002, US-PROF-002A, US-PROF-003, US-PROF-004, US-PROF-004A, US-PROF-005, US-PROF-006, US-PROF-006A, US-PROF-007 | 77 | 310 | Previous sprint deliverables, database/API contracts and QA environment. | Code reviewed, unit/API tests pass, RLS/security checks pass, Marathi/English labels complete, QA evidence attached and no open blocker.

## Sprint Story Map
storyId | epicId | epicName | description | priority | storyPoints | release | sprint | status
US-AUTH-001 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want signup with phone or email so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-002 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want login with password so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-002A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for login with password so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-003 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want PIN login so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-AUTH-004 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want forgot password so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-004A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for forgot password so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-005 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want reset password so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-006 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want logout current device so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-AUTH-006A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for logout current device so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-007 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want logout all devices so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-008 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want session expiry redirect so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-008A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for session expiry redirect so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-009 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want first-time language selection so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-010 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want language persistence after login so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-010A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for language persistence after login so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-011 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want multi-device login so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-012 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want account lockout so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-AUTH-012A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for account lockout so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-013 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want onboarding farm creation so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-014 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want profile creation after signup so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-014A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for profile creation after signup so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-015 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want existing user compatibility so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-AUTH-016 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want iOS session recovery so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-016A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for iOS session recovery so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-017 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want Android PWA login so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-018 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want admin login so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 1 | Sprint 1 | Backlog
US-AUTH-018A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for admin login so that mistakes are prevented before data is saved. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-019 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want support login so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-AUTH-020 | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want security audit logging so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-AUTH-020A | EPIC-AUTH | Authentication & Onboarding | As a farmer, I want validation and error handling for security audit logging so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-DASH-001 | EPIC-DASH | Home Dashboard | As a farmer, I want today milk summary so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-002 | EPIC-DASH | Home Dashboard | As a farmer, I want morning/evening split so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-002A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for morning/evening split so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-003 | EPIC-DASH | Home Dashboard | As a farmer, I want today income so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-DASH-004 | EPIC-DASH | Home Dashboard | As a farmer, I want pending slip banner so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-004A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for pending slip banner so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-005 | EPIC-DASH | Home Dashboard | As a farmer, I want quick actions so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-006 | EPIC-DASH | Home Dashboard | As a farmer, I want AI card so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 4 | Sprint 10 | Backlog
US-DASH-006A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for AI card so that mistakes are prevented before data is saved. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-007 | EPIC-DASH | Home Dashboard | As a farmer, I want goal progress so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-008 | EPIC-DASH | Home Dashboard | As a farmer, I want urgent reminders so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-008A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for urgent reminders so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-009 | EPIC-DASH | Home Dashboard | As a farmer, I want today reminders so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-DASH-010 | EPIC-DASH | Home Dashboard | As a farmer, I want upcoming reminders so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-010A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for upcoming reminders so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-011 | EPIC-DASH | Home Dashboard | As a farmer, I want recent activity so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-012 | EPIC-DASH | Home Dashboard | As a farmer, I want farm snapshot so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-DASH-012A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for farm snapshot so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-013 | EPIC-DASH | Home Dashboard | As a farmer, I want monthly performance so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-DASH-014 | EPIC-DASH | Home Dashboard | As a farmer, I want dairy score so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-014A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for dairy score so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-015 | EPIC-DASH | Home Dashboard | As a farmer, I want notification bell so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-DASH-016 | EPIC-DASH | Home Dashboard | As a farmer, I want skeleton loading so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-016A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for skeleton loading so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-017 | EPIC-DASH | Home Dashboard | As a farmer, I want offline state so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-018 | EPIC-DASH | Home Dashboard | As a farmer, I want light theme default so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-DASH-018A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for light theme default so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-019 | EPIC-DASH | Home Dashboard | As a farmer, I want mobile layout so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-DASH-020 | EPIC-DASH | Home Dashboard | As a farmer, I want refresh strategy so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-DASH-020A | EPIC-DASH | Home Dashboard | As a farmer, I want validation and error handling for refresh strategy so that mistakes are prevented before data is saved. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-FARM-001 | EPIC-FARM | Farm & Member Management | As a farmer, I want create farm so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-002 | EPIC-FARM | Farm & Member Management | As a farmer, I want edit farm name so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-FARM-002A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for edit farm name so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-003 | EPIC-FARM | Farm & Member Management | As a farmer, I want edit village/taluka/district so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-FARM-004 | EPIC-FARM | Farm & Member Management | As a farmer, I want member invite so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-004A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for member invite so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-005 | EPIC-FARM | Farm & Member Management | As a farmer, I want member role change so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-FARM-006 | EPIC-FARM | Farm & Member Management | As a farmer, I want member removal so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-FARM-006A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for member removal so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-007 | EPIC-FARM | Farm & Member Management | As a farmer, I want farm settings so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-008 | EPIC-FARM | Farm & Member Management | As a farmer, I want veterinarian list so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-FARM-008A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for veterinarian list so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-009 | EPIC-FARM | Farm & Member Management | As a farmer, I want farm permissions so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-FARM-010 | EPIC-FARM | Farm & Member Management | As a farmer, I want farm status so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-010A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for farm status so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-011 | EPIC-FARM | Farm & Member Management | As a farmer, I want trial status so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-FARM-012 | EPIC-FARM | Farm & Member Management | As a farmer, I want farm statistics so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-FARM-012A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for farm statistics so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-013 | EPIC-FARM | Farm & Member Management | As a farmer, I want farm profile completion so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-014 | EPIC-FARM | Farm & Member Management | As a farmer, I want storage paths so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-FARM-014A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for storage paths so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-FARM-015 | EPIC-FARM | Farm & Member Management | As a farmer, I want location dropdown so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-FARM-016 | EPIC-FARM | Farm & Member Management | As a farmer, I want subscription state so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 1 | Sprint 2 | Backlog
US-FARM-016A | EPIC-FARM | Farm & Member Management | As a farmer, I want validation and error handling for subscription state so that mistakes are prevented before data is saved. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-001 | EPIC-COW | Cow Management | As a farmer, I want add cow so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-002 | EPIC-COW | Cow Management | As a farmer, I want edit cow so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-002A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for edit cow so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-003 | EPIC-COW | Cow Management | As a farmer, I want archive cow so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-COW-004 | EPIC-COW | Cow Management | As a farmer, I want mark sold so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-004A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for mark sold so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-005 | EPIC-COW | Cow Management | As a farmer, I want cow profile so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-006 | EPIC-COW | Cow Management | As a farmer, I want cow photo so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-COW-006A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for cow photo so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-007 | EPIC-COW | Cow Management | As a farmer, I want breed selection so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-008 | EPIC-COW | Cow Management | As a farmer, I want tag number so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-008A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for tag number so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-009 | EPIC-COW | Cow Management | As a farmer, I want pregnancy status so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-COW-010 | EPIC-COW | Cow Management | As a farmer, I want AI record so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 1 | Sprint 2 | Backlog
US-COW-010A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for AI record so that mistakes are prevented before data is saved. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-011 | EPIC-COW | Cow Management | As a farmer, I want pregnancy check so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-012 | EPIC-COW | Cow Management | As a farmer, I want calving status so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-COW-012A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for calving status so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-013 | EPIC-COW | Cow Management | As a farmer, I want health history so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-014 | EPIC-COW | Cow Management | As a farmer, I want vaccination history so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-014A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for vaccination history so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-015 | EPIC-COW | Cow Management | As a farmer, I want important dates so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-COW-016 | EPIC-COW | Cow Management | As a farmer, I want cow timeline so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-016A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for cow timeline so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-COW-017 | EPIC-COW | Cow Management | As a farmer, I want sort pregnant cows by due date so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 2 | Backlog
US-COW-018 | EPIC-COW | Cow Management | As a farmer, I want fast detail navigation so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 2 | Backlog
US-COW-018A | EPIC-COW | Cow Management | As a farmer, I want validation and error handling for fast detail navigation so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 2 | Backlog
US-CALF-001 | EPIC-CALF | Calf Management | As a farmer, I want add calf so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-002 | EPIC-CALF | Calf Management | As a farmer, I want edit calf so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-CALF-002A | EPIC-CALF | Calf Management | As a farmer, I want validation and error handling for edit calf so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-003 | EPIC-CALF | Calf Management | As a farmer, I want sell calf so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-CALF-004 | EPIC-CALF | Calf Management | As a farmer, I want mark dead so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-004A | EPIC-CALF | Calf Management | As a farmer, I want validation and error handling for mark dead so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-005 | EPIC-CALF | Calf Management | As a farmer, I want convert female calf to cow so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-CALF-006 | EPIC-CALF | Calf Management | As a farmer, I want link mother cow so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-CALF-006A | EPIC-CALF | Calf Management | As a farmer, I want validation and error handling for link mother cow so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-007 | EPIC-CALF | Calf Management | As a farmer, I want calf photo so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-008 | EPIC-CALF | Calf Management | As a farmer, I want gender tracking so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-CALF-008A | EPIC-CALF | Calf Management | As a farmer, I want validation and error handling for gender tracking so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-009 | EPIC-CALF | Calf Management | As a farmer, I want dehorning reminder 30-45 days so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-CALF-010 | EPIC-CALF | Calf Management | As a farmer, I want weaning reminder so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-010A | EPIC-CALF | Calf Management | As a farmer, I want validation and error handling for weaning reminder so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-011 | EPIC-CALF | Calf Management | As a farmer, I want health records so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-CALF-012 | EPIC-CALF | Calf Management | As a farmer, I want vaccination records so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-CALF-012A | EPIC-CALF | Calf Management | As a farmer, I want validation and error handling for vaccination records so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-013 | EPIC-CALF | Calf Management | As a farmer, I want calf age display so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-014 | EPIC-CALF | Calf Management | As a farmer, I want suppress sold calf reminders so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-CALF-014A | EPIC-CALF | Calf Management | As a farmer, I want validation and error handling for suppress sold calf reminders so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-CALF-015 | EPIC-CALF | Calf Management | As a farmer, I want calf lifecycle audit so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-001 | EPIC-REC | Records Management | As a farmer, I want manual milk record so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-002 | EPIC-REC | Records Management | As a farmer, I want bulk milk record so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-002A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for bulk milk record so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-003 | EPIC-REC | Records Management | As a farmer, I want feed record so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-REC-004 | EPIC-REC | Records Management | As a farmer, I want feed expense impact so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-004A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for feed expense impact so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-005 | EPIC-REC | Records Management | As a farmer, I want health record so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-006 | EPIC-REC | Records Management | As a farmer, I want vaccination record so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-REC-006A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for vaccination record so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-007 | EPIC-REC | Records Management | As a farmer, I want deworming record so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-008 | EPIC-REC | Records Management | As a farmer, I want breeding record so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-008A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for breeding record so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-009 | EPIC-REC | Records Management | As a farmer, I want calving record so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-REC-010 | EPIC-REC | Records Management | As a farmer, I want record edit so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-010A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for record edit so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-011 | EPIC-REC | Records Management | As a farmer, I want record delete so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-012 | EPIC-REC | Records Management | As a farmer, I want duplicate prevention so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-REC-012A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for duplicate prevention so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-013 | EPIC-REC | Records Management | As a farmer, I want offline record queue so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-014 | EPIC-REC | Records Management | As a farmer, I want voice inputs so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-014A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for voice inputs so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-015 | EPIC-REC | Records Management | As a farmer, I want validation messages so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 3 | Backlog
US-REC-016 | EPIC-REC | Records Management | As a farmer, I want veterinarian dropdown so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-016A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for veterinarian dropdown so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REC-017 | EPIC-REC | Records Management | As a farmer, I want milk source type so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-018 | EPIC-REC | Records Management | As a farmer, I want record audit so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 3 | Backlog
US-REC-018A | EPIC-REC | Records Management | As a farmer, I want validation and error handling for record audit so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 3 | Backlog
US-REM-001 | EPIC-REM | Reminder Engine | As a farmer, I want pregnancy check reminder so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-002 | EPIC-REM | Reminder Engine | As a farmer, I want dry-off reminder so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 4 | Backlog
US-REM-002A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for dry-off reminder so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-003 | EPIC-REM | Reminder Engine | As a farmer, I want calving reminder so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 4 | Backlog
US-REM-004 | EPIC-REM | Reminder Engine | As a farmer, I want next breeding readiness reminder so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-004A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for next breeding readiness reminder so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-005 | EPIC-REM | Reminder Engine | As a farmer, I want missed pregnancy alert so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 4 | Backlog
US-REM-006 | EPIC-REM | Reminder Engine | As a farmer, I want repeat breeding alert so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 4 | Backlog
US-REM-006A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for repeat breeding alert so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-007 | EPIC-REM | Reminder Engine | As a farmer, I want vaccination reminder so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-008 | EPIC-REM | Reminder Engine | As a farmer, I want deworming reminder so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 4 | Backlog
US-REM-008A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for deworming reminder so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-009 | EPIC-REM | Reminder Engine | As a farmer, I want dehorning reminder so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 4 | Backlog
US-REM-010 | EPIC-REM | Reminder Engine | As a farmer, I want weaning reminder so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-010A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for weaning reminder so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-011 | EPIC-REM | Reminder Engine | As a farmer, I want custom reminder so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 4 | Backlog
US-REM-012 | EPIC-REM | Reminder Engine | As a farmer, I want snooze reminder so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 4 | Backlog
US-REM-012A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for snooze reminder so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-013 | EPIC-REM | Reminder Engine | As a farmer, I want complete reminder so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-014 | EPIC-REM | Reminder Engine | As a farmer, I want cancel lifecycle reminders so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 4 | Backlog
US-REM-014A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for cancel lifecycle reminders so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-015 | EPIC-REM | Reminder Engine | As a farmer, I want slip upload banner not reminder so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 4 | Backlog
US-REM-016 | EPIC-REM | Reminder Engine | As a farmer, I want reminder filters so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-016A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for reminder filters so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-REM-017 | EPIC-REM | Reminder Engine | As a farmer, I want home reminder summary so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 4 | Backlog
US-REM-018 | EPIC-REM | Reminder Engine | As a farmer, I want notification integration so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 4 | Backlog
US-REM-018A | EPIC-REM | Reminder Engine | As a farmer, I want validation and error handling for notification integration so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 4 | Backlog
US-ACC-001 | EPIC-ACC | Accounting & Settlement | As a farmer, I want daily milk accounting so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-002 | EPIC-ACC | Accounting & Settlement | As a farmer, I want 15-day settlement manual entry so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 2 | Sprint 5 | Backlog
US-ACC-002A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for 15-day settlement manual entry so that mistakes are prevented before data is saved. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-003 | EPIC-ACC | Accounting & Settlement | As a farmer, I want settlement OCR save so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 2 | Sprint 5 | Backlog
US-ACC-004 | EPIC-ACC | Accounting & Settlement | As a farmer, I want feed deduction as expense so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-004A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for feed deduction as expense so that mistakes are prevented before data is saved. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-005 | EPIC-ACC | Accounting & Settlement | As a farmer, I want manual feed expense inclusion so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-006 | EPIC-ACC | Accounting & Settlement | As a farmer, I want other expense so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 2 | Sprint 5 | Backlog
US-ACC-006A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for other expense so that mistakes are prevented before data is saved. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-007 | EPIC-ACC | Accounting & Settlement | As a farmer, I want income entry so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-008 | EPIC-ACC | Accounting & Settlement | As a farmer, I want profit calculation so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-008A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for profit calculation so that mistakes are prevented before data is saved. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-009 | EPIC-ACC | Accounting & Settlement | As a farmer, I want monthly summary so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 2 | Sprint 5 | Backlog
US-ACC-010 | EPIC-ACC | Accounting & Settlement | As a farmer, I want annual summary so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-010A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for annual summary so that mistakes are prevented before data is saved. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-011 | EPIC-ACC | Accounting & Settlement | As a farmer, I want payment status so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-012 | EPIC-ACC | Accounting & Settlement | As a farmer, I want settlement deletion reversal so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 2 | Sprint 5 | Backlog
US-ACC-012A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for settlement deletion reversal so that mistakes are prevented before data is saved. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-013 | EPIC-ACC | Accounting & Settlement | As a farmer, I want source of truth rules so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-014 | EPIC-ACC | Accounting & Settlement | As a farmer, I want morning/evening settlement totals so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 2 | Sprint 5 | Backlog
US-ACC-014A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for morning/evening settlement totals so that mistakes are prevented before data is saved. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-015 | EPIC-ACC | Accounting & Settlement | As a farmer, I want dairy slips list so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 2 | Sprint 5 | Backlog
US-ACC-016 | EPIC-ACC | Accounting & Settlement | As a farmer, I want date filters so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-016A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for date filters so that mistakes are prevented before data is saved. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-ACC-017 | EPIC-ACC | Accounting & Settlement | As a farmer, I want financial audit so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-018 | EPIC-ACC | Accounting & Settlement | As a farmer, I want report reconciliation so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 2 | Sprint 5 | Backlog
US-ACC-018A | EPIC-ACC | Accounting & Settlement | As a farmer, I want validation and error handling for report reconciliation so that mistakes are prevented before data is saved. | Must | 3 | Release 2 | Sprint 5 | Backlog
US-OCR-001 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want native camera upload so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-002 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want gallery upload so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-002A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for gallery upload so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-003 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want client compression so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 6 | Backlog
US-OCR-004 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want clear daily slip extraction so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-004A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for clear daily slip extraction so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-005 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want poor image warning so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-006 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want settlement extraction so that I can use Majhi Dairy effectively and accurately. | Should | 13 | Release 2 | Sprint 6 | Backlog
US-OCR-006A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for settlement extraction so that mistakes are prevented before data is saved. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-007 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want morning/evening table extraction so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-008 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want OCR fallback to direct GPT so that I can use Majhi Dairy effectively and accurately. | Should | 8 | Release 2 | Sprint 6 | Backlog
US-OCR-008A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for OCR fallback to direct GPT so that mistakes are prevented before data is saved. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-009 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want manual review so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 6 | Backlog
US-OCR-010 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want confidence indicators so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-010A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for confidence indicators so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-011 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want duplicate slip detection so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-012 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want save daily slip so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 6 | Backlog
US-OCR-012A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for save daily slip so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-013 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want save settlement slip so that I can use Majhi Dairy effectively and accurately. | Should | 8 | Release 2 | Sprint 6 | Backlog
US-OCR-014 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want retry scan so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-014A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for retry scan so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-015 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want audit log so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-016 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want offline capture so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-016A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for offline capture so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-OCR-017 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want provider billing error handling so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 6 | Backlog
US-OCR-018 | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want JSON repair so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 6 | Backlog
US-OCR-018A | EPIC-OCR | AI Slip Scanning & OCR | As a farmer, I want validation and error handling for JSON repair so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 6 | Backlog
US-REP-001 | EPIC-REP | Reports & Analytics | As a farmer, I want milk report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-002 | EPIC-REP | Reports & Analytics | As a farmer, I want income report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-002A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for income report so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-003 | EPIC-REP | Reports & Analytics | As a farmer, I want expense report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-004 | EPIC-REP | Reports & Analytics | As a farmer, I want profit report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-004A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for profit report so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-005 | EPIC-REP | Reports & Analytics | As a farmer, I want annual report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-006 | EPIC-REP | Reports & Analytics | As a farmer, I want cow performance report so that I can use Majhi Dairy effectively and accurately. | Should | 13 | Release 2 | Sprint 7 | Backlog
US-REP-006A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for cow performance report so that mistakes are prevented before data is saved. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-007 | EPIC-REP | Reports & Analytics | As a farmer, I want vaccination report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-008 | EPIC-REP | Reports & Analytics | As a farmer, I want settlement report so that I can use Majhi Dairy effectively and accurately. | Should | 8 | Release 2 | Sprint 7 | Backlog
US-REP-008A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for settlement report so that mistakes are prevented before data is saved. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-009 | EPIC-REP | Reports & Analytics | As a farmer, I want print report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-010 | EPIC-REP | Reports & Analytics | As a farmer, I want PDF export so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-010A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for PDF export so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-011 | EPIC-REP | Reports & Analytics | As a farmer, I want Excel export so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-012 | EPIC-REP | Reports & Analytics | As a farmer, I want CSV export so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 7 | Backlog
US-REP-012A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for CSV export so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-013 | EPIC-REP | Reports & Analytics | As a farmer, I want Marathi report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-014 | EPIC-REP | Reports & Analytics | As a farmer, I want English report so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-014A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for English report so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-015 | EPIC-REP | Reports & Analytics | As a farmer, I want filters so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 7 | Backlog
US-REP-016 | EPIC-REP | Reports & Analytics | As a farmer, I want charts so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-016A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for charts so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-REP-017 | EPIC-REP | Reports & Analytics | As a farmer, I want monthly comparison so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 7 | Backlog
US-REP-018 | EPIC-REP | Reports & Analytics | As a farmer, I want data source reconciliation so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 7 | Backlog
US-REP-018A | EPIC-REP | Reports & Analytics | As a farmer, I want validation and error handling for data source reconciliation so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 7 | Backlog
US-AI-001 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want open AI chat so that I can use Majhi Dairy effectively and accurately. | Should | 8 | Release 3 | Sprint 6 | Backlog
US-AI-002 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want ask today milk so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 6 | Backlog
US-AI-002A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for ask today milk so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-003 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want ask monthly income so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 6 | Backlog
US-AI-004 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want average fat so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-004A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for average fat so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-005 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want highest milk day so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 6 | Backlog
US-AI-006 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want permissions so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 6 | Backlog
US-AI-006A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for permissions so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-007 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want disable AI so that I can use Majhi Dairy effectively and accurately. | Should | 8 | Release 3 | Sprint 6 | Backlog
US-AI-008 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want response style short so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 6 | Backlog
US-AI-008A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for response style short so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-009 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want response style detailed so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 6 | Backlog
US-AI-010 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want response style expert so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-010A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for response style expert so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-011 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want chat history so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 6 | Backlog
US-AI-012 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want delete chat so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 6 | Backlog
US-AI-012A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for delete chat so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-013 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want feedback so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-014 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want Marathi answer so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 6 | Backlog
US-AI-014A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for Marathi answer so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-015 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want English answer so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 6 | Backlog
US-AI-016 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want no hallucination so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-016A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for no hallucination so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-AI-017 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want tool audit so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 6 | Backlog
US-AI-018 | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want token tracking so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 6 | Backlog
US-AI-018A | EPIC-AI | Dugdhmitra AI Assistant | As a farmer, I want validation and error handling for token tracking so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 6 | Backlog
US-NOTIF-001 | EPIC-NOTIF | Notifications | As a farmer, I want notification inbox so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-002 | EPIC-NOTIF | Notifications | As a farmer, I want mark read so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-002A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for mark read so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-003 | EPIC-NOTIF | Notifications | As a farmer, I want mark all read so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 4 | Backlog
US-NOTIF-004 | EPIC-NOTIF | Notifications | As a farmer, I want delete notification so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-004A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for delete notification so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-005 | EPIC-NOTIF | Notifications | As a farmer, I want push registration so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-006 | EPIC-NOTIF | Notifications | As a farmer, I want test notification so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 4 | Backlog
US-NOTIF-006A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for test notification so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-007 | EPIC-NOTIF | Notifications | As a farmer, I want notification preferences so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-008 | EPIC-NOTIF | Notifications | As a farmer, I want quiet hours so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-008A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for quiet hours so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-009 | EPIC-NOTIF | Notifications | As a farmer, I want admin broadcast so that I can use Majhi Dairy effectively and accurately. | Should | 13 | Release 2 | Sprint 4 | Backlog
US-NOTIF-010 | EPIC-NOTIF | Notifications | As a farmer, I want reminder notification so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-010A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for reminder notification so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-011 | EPIC-NOTIF | Notifications | As a farmer, I want goal notification so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-012 | EPIC-NOTIF | Notifications | As a farmer, I want subscription notification so that I can use Majhi Dairy effectively and accurately. | Should | 13 | Release 2 | Sprint 4 | Backlog
US-NOTIF-012A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for subscription notification so that mistakes are prevented before data is saved. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-013 | EPIC-NOTIF | Notifications | As a farmer, I want push retry so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-014 | EPIC-NOTIF | Notifications | As a farmer, I want invalid subscription cleanup so that I can use Majhi Dairy effectively and accurately. | Should | 8 | Release 2 | Sprint 4 | Backlog
US-NOTIF-014A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for invalid subscription cleanup so that mistakes are prevented before data is saved. | Should | 5 | Release 2 | Sprint 4 | Backlog
US-NOTIF-015 | EPIC-NOTIF | Notifications | As a farmer, I want notification tone so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 2 | Sprint 4 | Backlog
US-NOTIF-016 | EPIC-NOTIF | Notifications | As a farmer, I want voice off so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-NOTIF-016A | EPIC-NOTIF | Notifications | As a farmer, I want validation and error handling for voice off so that mistakes are prevented before data is saved. | Should | 3 | Release 2 | Sprint 4 | Backlog
US-SET-001 | EPIC-SET | Settings & Personalization | As a farmer, I want settings home so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-002 | EPIC-SET | Settings & Personalization | As a farmer, I want profile settings so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-SET-002A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for profile settings so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-003 | EPIC-SET | Settings & Personalization | As a farmer, I want security settings so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-SET-004 | EPIC-SET | Settings & Personalization | As a farmer, I want notification settings so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-004A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for notification settings so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-005 | EPIC-SET | Settings & Personalization | As a farmer, I want language settings so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-SET-006 | EPIC-SET | Settings & Personalization | As a farmer, I want theme settings so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-SET-006A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for theme settings so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-007 | EPIC-SET | Settings & Personalization | As a farmer, I want font size so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-008 | EPIC-SET | Settings & Personalization | As a farmer, I want compact mode so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-SET-008A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for compact mode so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-009 | EPIC-SET | Settings & Personalization | As a farmer, I want high contrast so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-SET-010 | EPIC-SET | Settings & Personalization | As a farmer, I want large touch targets so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-010A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for large touch targets so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-011 | EPIC-SET | Settings & Personalization | As a farmer, I want reduce animations so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-SET-012 | EPIC-SET | Settings & Personalization | As a farmer, I want AI settings so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 1 | Sprint 1 | Backlog
US-SET-012A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for AI settings so that mistakes are prevented before data is saved. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-SET-013 | EPIC-SET | Settings & Personalization | As a farmer, I want goals settings so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-014 | EPIC-SET | Settings & Personalization | As a farmer, I want export settings so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 1 | Sprint 1 | Backlog
US-SET-014A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for export settings so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-015 | EPIC-SET | Settings & Personalization | As a farmer, I want veterinarian settings so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 1 | Sprint 1 | Backlog
US-SET-016 | EPIC-SET | Settings & Personalization | As a farmer, I want save preferences so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-SET-016A | EPIC-SET | Settings & Personalization | As a farmer, I want validation and error handling for save preferences so that mistakes are prevented before data is saved. | Must | 3 | Release 1 | Sprint 1 | Backlog
US-PROF-001 | EPIC-PROF | Profile & Statistics | As a farmer, I want profile page so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-002 | EPIC-PROF | Profile & Statistics | As a farmer, I want profile photo so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 10 | Backlog
US-PROF-002A | EPIC-PROF | Profile & Statistics | As a farmer, I want validation and error handling for profile photo so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-003 | EPIC-PROF | Profile & Statistics | As a farmer, I want edit personal info so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 10 | Backlog
US-PROF-004 | EPIC-PROF | Profile & Statistics | As a farmer, I want edit farm name so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-004A | EPIC-PROF | Profile & Statistics | As a farmer, I want validation and error handling for edit farm name so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-005 | EPIC-PROF | Profile & Statistics | As a farmer, I want village/taluka dropdown so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 10 | Backlog
US-PROF-006 | EPIC-PROF | Profile & Statistics | As a farmer, I want statistics dashboard so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 10 | Backlog
US-PROF-006A | EPIC-PROF | Profile & Statistics | As a farmer, I want validation and error handling for statistics dashboard so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-007 | EPIC-PROF | Profile & Statistics | As a farmer, I want dairy score page so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-008 | EPIC-PROF | Profile & Statistics | As a farmer, I want achievements page so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 10 | Backlog
US-PROF-008A | EPIC-PROF | Profile & Statistics | As a farmer, I want validation and error handling for achievements page so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-009 | EPIC-PROF | Profile & Statistics | As a farmer, I want member since so that I can use Majhi Dairy effectively and accurately. | Should | 2 | Release 3 | Sprint 10 | Backlog
US-PROF-010 | EPIC-PROF | Profile & Statistics | As a farmer, I want farm statistics so that I can use Majhi Dairy effectively and accurately. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-010A | EPIC-PROF | Profile & Statistics | As a farmer, I want validation and error handling for farm statistics so that mistakes are prevented before data is saved. | Should | 3 | Release 3 | Sprint 10 | Backlog
US-PROF-011 | EPIC-PROF | Profile & Statistics | As a farmer, I want profile menu close on outside click so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 10 | Backlog
US-PROF-012 | EPIC-PROF | Profile & Statistics | As a farmer, I want language preference display so that I can use Majhi Dairy effectively and accurately. | Should | 5 | Release 3 | Sprint 10 | Backlog
US-SUP-001 | EPIC-SUP | Support Center | As a support user, I want help home so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 8 | Backlog
US-SUP-002 | EPIC-SUP | Support Center | As a support user, I want FAQ search so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 8 | Backlog
US-SUP-003 | EPIC-SUP | Support Center | As a support user, I want tutorials so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 8 | Backlog
US-SUP-004 | EPIC-SUP | Support Center | As a support user, I want create ticket so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 8 | Backlog
US-SUP-005 | EPIC-SUP | Support Center | As a support user, I want reply ticket so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 8 | Backlog
US-SUP-006 | EPIC-SUP | Support Center | As a support user, I want upload attachment so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 8 | Backlog
US-SUP-007 | EPIC-SUP | Support Center | As a support user, I want close ticket so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 8 | Backlog
US-SUP-008 | EPIC-SUP | Support Center | As a support user, I want reopen ticket so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 8 | Backlog
US-SUP-009 | EPIC-SUP | Support Center | As a support user, I want support rating so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 8 | Backlog
US-SUP-010 | EPIC-SUP | Support Center | As a support user, I want bug report so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 8 | Backlog
US-SUP-011 | EPIC-SUP | Support Center | As a support user, I want feature request so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 8 | Backlog
US-SUP-012 | EPIC-SUP | Support Center | As a support user, I want contact options so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 8 | Backlog
US-SUP-013 | EPIC-SUP | Support Center | As a support user, I want system status so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 8 | Backlog
US-SUP-014 | EPIC-SUP | Support Center | As a support user, I want admin reply notification so that I can use Majhi Dairy effectively and accurately. | Could | 8 | Release 3 | Sprint 8 | Backlog
US-ACH-001 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want achievement dashboard so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 9 | Backlog
US-ACH-002 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want milk production badge so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 9 | Backlog
US-ACH-003 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want income badge so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 9 | Backlog
US-ACH-004 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want OCR badge so that I can use Majhi Dairy effectively and accurately. | Could | 8 | Release 3 | Sprint 9 | Backlog
US-ACH-005 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want AI badge so that I can use Majhi Dairy effectively and accurately. | Could | 8 | Release 3 | Sprint 9 | Backlog
US-ACH-006 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want consistency streak so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 9 | Backlog
US-ACH-007 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want farm growth badge so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 9 | Backlog
US-ACH-008 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want dairy score so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 9 | Backlog
US-ACH-009 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want rank page so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 9 | Backlog
US-ACH-010 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want leaderboard all farms so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 9 | Backlog
US-ACH-011 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want leaderboard taluka so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 9 | Backlog
US-ACH-012 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want share achievement so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 9 | Backlog
US-ACH-013 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want confetti so that I can use Majhi Dairy effectively and accurately. | Could | 3 | Release 3 | Sprint 9 | Backlog
US-ACH-014 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want achievement notification so that I can use Majhi Dairy effectively and accurately. | Could | 5 | Release 3 | Sprint 9 | Backlog
US-ACH-015 | EPIC-ACH | Achievements & Leaderboard | As a farmer, I want score recalculation so that I can use Majhi Dairy effectively and accurately. | Could | 2 | Release 3 | Sprint 9 | Backlog
US-ADMIN-001 | EPIC-ADMIN | Admin Panel | As a administrator, I want admin dashboard so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 4 | Sprint 8 | Backlog
US-ADMIN-002 | EPIC-ADMIN | Admin Panel | As a administrator, I want user list so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 8 | Backlog
US-ADMIN-003 | EPIC-ADMIN | Admin Panel | As a administrator, I want farm list so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 8 | Backlog
US-ADMIN-004 | EPIC-ADMIN | Admin Panel | As a administrator, I want farm details so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 8 | Backlog
US-ADMIN-005 | EPIC-ADMIN | Admin Panel | As a administrator, I want farm health score so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 8 | Backlog
US-ADMIN-006 | EPIC-ADMIN | Admin Panel | As a administrator, I want device details so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 8 | Backlog
US-ADMIN-007 | EPIC-ADMIN | Admin Panel | As a administrator, I want subscription control so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 4 | Sprint 8 | Backlog
US-ADMIN-008 | EPIC-ADMIN | Admin Panel | As a administrator, I want trial reduce/extend so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 8 | Backlog
US-ADMIN-009 | EPIC-ADMIN | Admin Panel | As a administrator, I want suspend farm so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 8 | Backlog
US-ADMIN-010 | EPIC-ADMIN | Admin Panel | As a administrator, I want activate farm so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 8 | Backlog
US-ADMIN-011 | EPIC-ADMIN | Admin Panel | As a administrator, I want admin notification center so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 4 | Sprint 8 | Backlog
US-ADMIN-012 | EPIC-ADMIN | Admin Panel | As a administrator, I want template edit/delete so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 8 | Backlog
US-ADMIN-013 | EPIC-ADMIN | Admin Panel | As a administrator, I want support admin so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 4 | Sprint 8 | Backlog
US-ADMIN-014 | EPIC-ADMIN | Admin Panel | As a administrator, I want audit logs so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 8 | Backlog
US-ADMIN-015 | EPIC-ADMIN | Admin Panel | As a administrator, I want analytics so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 8 | Backlog
US-ADMIN-016 | EPIC-ADMIN | Admin Panel | As a administrator, I want export farm data so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 8 | Backlog
US-ADMIN-017 | EPIC-ADMIN | Admin Panel | As a administrator, I want protected delete so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 8 | Backlog
US-QA-001 | EPIC-QA | Quality, Security & Performance | As a farmer, I want unit test setup so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-QA-002 | EPIC-QA | Quality, Security & Performance | As a farmer, I want API contract tests so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-QA-003 | EPIC-QA | Quality, Security & Performance | As a farmer, I want RLS tests so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 4 | Sprint 9 | Backlog
US-QA-004 | EPIC-QA | Quality, Security & Performance | As a farmer, I want financial regression so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-QA-005 | EPIC-QA | Quality, Security & Performance | As a farmer, I want OCR regression so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-QA-006 | EPIC-QA | Quality, Security & Performance | As a farmer, I want AI permission tests so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 4 | Sprint 9 | Backlog
US-QA-007 | EPIC-QA | Quality, Security & Performance | As a farmer, I want localization audit so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-QA-008 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA testing so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-QA-009 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA testing so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-QA-010 | EPIC-QA | Quality, Security & Performance | As a farmer, I want performance optimization so that I can use Majhi Dairy effectively and accurately. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-QA-011 | EPIC-QA | Quality, Security & Performance | As a farmer, I want security scan so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-QA-012 | EPIC-QA | Quality, Security & Performance | As a farmer, I want UAT scripts so that I can use Majhi Dairy effectively and accurately. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-QA-013 | EPIC-QA | Quality, Security & Performance | As a farmer, I want release checklist so that I can use Majhi Dairy effectively and accurately. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-QA-014 | EPIC-QA | Quality, Security & Performance | As a farmer, I want monitoring so that I can use Majhi Dairy effectively and accurately. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-QA-015 | EPIC-QA | Quality, Security & Performance | As a farmer, I want backup restore drill so that I can use Majhi Dairy effectively and accurately. | Must | 13 | Release 4 | Sprint 9 | Backlog
US-X-001 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 1 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-002 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 2 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-003 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 3 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-004 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 4 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-005 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 5 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-006 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 6 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-007 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 7 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-008 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 8 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-009 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 9 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-010 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 10 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-011 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 11 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-012 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 12 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-013 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 13 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-014 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 14 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-015 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 15 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-016 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 16 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-017 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 17 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-018 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 18 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-019 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 19 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-020 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 20 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-021 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 21 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-022 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 22 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-023 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 23 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-024 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 24 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-025 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 25 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-026 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 26 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-027 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 27 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-028 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 28 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-029 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 29 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-030 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 30 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-031 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 31 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-032 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 32 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-033 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 33 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-034 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 34 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-035 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 35 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-036 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 36 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-037 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 37 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-038 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 38 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-039 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 39 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-040 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 40 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-041 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 41 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-042 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 42 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-043 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 43 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-044 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 44 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-045 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 45 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-046 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 46 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-047 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 47 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 9 | Backlog
US-X-048 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 48 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 9 | Backlog
US-X-049 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 49 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 9 | Backlog
US-X-050 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 50 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 9 | Backlog
US-X-051 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 51 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-052 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 52 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-X-053 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 53 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-X-054 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 54 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-X-055 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 55 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-056 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 56 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-X-057 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 57 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-X-058 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 58 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-X-059 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 59 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-060 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 60 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-X-061 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 61 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-X-062 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 62 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-X-063 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 63 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-064 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 64 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-X-065 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 65 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-X-066 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 66 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-X-067 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 67 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-068 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 68 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-X-069 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 69 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-X-070 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 70 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-X-071 | EPIC-QA | Quality, Security & Performance | As a administrator, I want cross-farm access prevention scenario 71 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-072 | EPIC-QA | Quality, Security & Performance | As a administrator, I want audit log verification scenario 72 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-X-073 | EPIC-SET | Settings & Personalization | As a farmer, I want Marathi and English text review scenario 73 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-X-074 | EPIC-QA | Quality, Security & Performance | As a farmer, I want home page sub-second perceived load scenario 74 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-X-075 | EPIC-QA | Quality, Security & Performance | As a farmer, I want offline queue conflict resolution scenario 75 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-076 | EPIC-QA | Quality, Security & Performance | As a farmer, I want iOS PWA session stability scenario 76 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog
US-X-077 | EPIC-QA | Quality, Security & Performance | As a farmer, I want Android PWA install and push flow scenario 77 verified so that launch quality is protected. | Must | 3 | Release 4 | Sprint 10 | Backlog
US-X-078 | EPIC-QA | Quality, Security & Performance | As a developer, I want database migration rollback scenario 78 verified so that launch quality is protected. | Must | 5 | Release 4 | Sprint 10 | Backlog
US-X-079 | EPIC-QA | Quality, Security & Performance | As a developer, I want monitoring and alerting scenario 79 verified so that launch quality is protected. | Must | 8 | Release 4 | Sprint 10 | Backlog
US-X-080 | EPIC-QA | Quality, Security & Performance | As a administrator, I want backup restore drill scenario 80 verified so that launch quality is protected. | Must | 2 | Release 4 | Sprint 10 | Backlog