## Roadmap Dashboard
metric | value
Roadmap phases | 16
Sprints including Sprint 0 | 21
Epics | 22
Stories | 480
Total story points | 2317

## Sprint Dashboard
sprint | theme | storyCount | storyPoints
Sprint 0 | Project Setup | 25 | 100
Sprint 1 | Authentication + Language Selection | 20 | 88
Sprint 2 | Farm Management | 40 | 176
Sprint 3 | Cow Management | 20 | 88
Sprint 4 | Calf Management | 20 | 88
Sprint 5 | Milk Records | 20 | 88
Sprint 6 | Reminders + Vaccinations | 20 | 88
Sprint 7 | Accounting | 20 | 148
Sprint 8 | OCR | 25 | 175
Sprint 9 | AI Assistant | 25 | 100
Sprint 10 | Reports | 20 | 88
Sprint 11 | Notifications | 25 | 100
Sprint 12 | Settings + Profile | 20 | 88
Sprint 13 | Support + Achievements | 40 | 176
Sprint 14 | Admin Panel | 25 | 175
Sprint 15 | Security Hardening | 25 | 175
Sprint 16 | Performance Optimization | 25 | 100
Sprint 17 | Bug Fixes + Regression | 20 | 88
Sprint 18 | UAT Support | 20 | 88
Sprint 19 | Release Preparation | 18 | 80
Sprint 20 | Production Launch | 7 | 27

## Release Dashboard
releaseId | releaseType | targetWindow | scope | entryCriteria | exitCriteria
R0 | Internal Alpha | After Sprint 5 | Auth, farm, cow, calf and milk records | Core workflows testable | No blocker in core data creation
R1 | MVP Beta | After Sprint 10 | Records, reminders, accounting, OCR, AI, reports | Financial/OCR/AI flows ready | Pilot farms can complete key workflows
R2 | Pilot Candidate | After Sprint 16 | Notifications, settings, support, achievements, admin, security/performance | Feature complete | Security/performance gates pass
R3 | Production Release | After Sprint 20 | Regression fixes, UAT support, release prep and launch | UAT pass >=95% | Go-live approval signed
Hotfix | Patch/Hotfix | As needed | Critical production defects only | Approved incident/defect | Fix verified and monitored

## Risk Dashboard
riskId | risk | category | probability | impact | mitigation | owner | status
DEV-RISK-001 | Financial calculation regression | Technical | Medium | Critical | Automated financial regression and settlement reconciliation | Engineering/QA | Open
DEV-RISK-002 | Cross-farm data leakage | Security | Low | Critical | RLS tests, service API guard and security review | Security/Backend | Open
DEV-RISK-003 | OCR accuracy below target | OCR | Medium | High | Golden slip set, fallback/manual review and provider monitoring | AI/OCR Engineer | Open
DEV-RISK-004 | AI hallucination or unauthorized data usage | AI | Medium | High | Function calling only, permission checks and answer verification tests | AI Engineer | Open
DEV-RISK-005 | iOS PWA instability | Technical | Medium | High | Dedicated iOS regression and session/storage QA | Frontend/QA | Open
DEV-RISK-006 | Push notification unreliability | Technical | Medium | Medium | Subscription diagnostics, fallback in-app notifications | Frontend/DevOps | Open
DEV-RISK-007 | Admin protected action misuse | Security | Low | High | Confirmation, reason, audit and role checks | Admin/Backend | Open
DEV-RISK-008 | Performance misses home/report targets | Performance | Medium | High | Caching, query indexes and budget monitoring | Engineering | Open
DEV-RISK-009 | Scope creep across settings/support/gamification | Delivery | High | Medium | MoSCoW prioritization and sprint change control | PM | Open
DEV-RISK-010 | Provider key/billing issue | Architecture | Medium | High | Provider config validation, quotas, fallback manual path | DevOps | Open
DEV-RISK-011 | UAT defects late in release | Delivery | Medium | High | Early pilot walkthroughs and sprint demos | QA/UAT Lead | Open
DEV-RISK-012 | Insufficient test data | QA | Medium | Medium | Seed scripts and golden datasets | QA/Data | Open

## Resource Dashboard
option | roles | capacity | velocity | responsibilities | risks
Solo Founder | Full-stack engineer + PM/QA/support | 20-35 hrs/week | 15-25 points/sprint | Build highest-priority features, manual QA, deployment, support | Context switching, slower QA/security coverage
2-4 Member Startup Team | Full-stack, frontend, QA/product, part-time DevOps | 80-140 hrs/week | 45-75 points/sprint | Parallel frontend/backend/QA delivery | Need tighter backlog grooming and integration discipline
5-10 Member Product Team | PM, designer, frontend, backend, QA automation, DevOps, support | 200-350 hrs/week | 100-180 points/sprint | Feature squads, automation, security/performance in parallel | Coordination overhead and dependency management