## Epics
epicId | epicName | businessObjective | technicalObjective | dependencies | acceptanceCriteria | riskLevel | estimatedEffortPoints | targetSprint | status
EPIC-SETUP | Project Setup | Establish repository, environments, CI/CD and engineering standards. | Create deployable technical foundation. |  | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Low | 55 | Sprint 0 | Planned
EPIC-AUTH | Authentication | Enable secure access, onboarding and language selection. | Supabase Auth, sessions, PIN, language persistence. | SETUP | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 110 | Sprint 1 | Planned
EPIC-FARM | Farm Management | Create and manage farm tenant profile, members and locations. | Farm schema, members, permissions and location dropdowns. | AUTH | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 95 | Sprint 2 | Planned
EPIC-DASH | Dashboard | Show most important farm status immediately. | Optimized home APIs, cached summaries and responsive cards. | AUTH,FARM | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Medium | 85 | Sprint 2 | Planned
EPIC-COW | Cow Management | Manage cow lifecycle, status and history. | Cow CRUD, profile, timeline and lifecycle rules. | FARM | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 120 | Sprint 3 | Planned
EPIC-CALF | Calf Management | Manage calf lifecycle, reminders and conversion/sale states. | Calf CRUD, mother linking, age/reminder logic. | COW | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 95 | Sprint 4 | Planned
EPIC-REC | Records | Capture milk, feed, health, vaccination, breeding and calving records. | Record APIs, validation, offline-safe mutations and audit. | COW,CALF | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 135 | Sprint 5 | Planned
EPIC-REM | Reminders | Generate and complete accurate animal and farm reminders. | Reminder engine, notification hooks and lifecycle cancellation. | REC | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 120 | Sprint 6 | Planned
EPIC-ACC | Accounting | Provide accurate milk, expense, settlement and profit accounting. | Financial schema, source-of-truth rules and reconciliation. | REC | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Critical | 160 | Sprint 7 | Planned
EPIC-OCR | OCR | Process daily and settlement dairy slips with user review. | Upload, compression, OCR/AI extraction, validation and audit. | ACC | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Critical | 145 | Sprint 8 | Planned
EPIC-AI | AI Assistant | Answer farm questions using real permitted database data. | Function-calling tools, permissions, history and settings. | REC,ACC | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 130 | Sprint 9 | Planned
EPIC-REP | Reports | Generate business, animal and financial reports. | Report APIs, charts, exports and print layouts. | ACC,REC | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 125 | Sprint 10 | Planned
EPIC-NOTIF | Notifications | Deliver in-app and push notifications reliably. | Inbox, preferences, push subscription and admin broadcasts. | REM | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 105 | Sprint 11 | Planned
EPIC-SET-PROF | Settings + Profile | Allow users to personalize, secure and manage their profile. | Settings APIs, profile, appearance, language and security UX. | AUTH,FARM | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Medium | 110 | Sprint 12 | Planned
EPIC-SUP | Support | Enable self-service help and support ticket workflows. | FAQ, tickets, attachments and support notifications. | AUTH | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Medium | 85 | Sprint 13 | Planned
EPIC-ACH | Achievements | Increase engagement through score, badges and leaderboard. | Achievement engine, score and ranking refresh. | REC,GOAL | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Medium | 80 | Sprint 13 | Planned
EPIC-ADMIN | Admin Panel | Give platform team farm monitoring and operations control. | Admin dashboards, farm details, subscriptions and audit. | AUTH,FARM,ACC | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Critical | 175 | Sprint 14 | Planned
EPIC-SEC | Security Hardening | Harden auth, RLS, storage, API, AI/OCR and admin actions. | Security tests, RLS validation, secrets, hardening checklist. | ALL | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Critical | 120 | Sprint 15 | Planned
EPIC-PERF | Performance Optimization | Meet page/API/report/OCR/AI performance targets. | Profiling, caching, query tuning and bundle optimization. | ALL | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 105 | Sprint 16 | Planned
EPIC-REG | Bug Fixes + Regression | Stabilize release candidate with regression coverage. | Bug triage, automated regression and defect burn-down. | ALL | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | High | 90 | Sprint 17 | Planned
EPIC-UAT | UAT Support | Support business users through UAT and pilot preparation. | UAT fixes, training support and acceptance evidence. | REG | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Medium | 75 | Sprint 18 | Planned
EPIC-REL | Production Release | Launch production with monitoring, rollback and hypercare. | Release runbook, migration, launch and hypercare execution. | UAT,SEC,PERF | Feature works end-to-end, tests pass, RLS/authorization verified, Marathi/English UX validated and no Critical/High defect remains. | Critical | 80 | Sprint 19 | Planned

## Feature Breakdown
featureId | epicId | epicName | feature | subFeatures | technicalTasks | backendTasks | frontendTasks | databaseTasks | qaTasks | devOpsTasks
EPIC-SETUP-F01 | EPIC-SETUP | Project Setup | Repository standards | Repository standards UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SETUP-F02 | EPIC-SETUP | Project Setup | Environment configuration | Environment configuration UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SETUP-F03 | EPIC-SETUP | Project Setup | CI/CD pipeline | CI/CD pipeline UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SETUP-F04 | EPIC-SETUP | Project Setup | Coding conventions | Coding conventions UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SETUP-F05 | EPIC-SETUP | Project Setup | Observability baseline | Observability baseline UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AUTH-F01 | EPIC-AUTH | Authentication | Signup | Signup UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AUTH-F02 | EPIC-AUTH | Authentication | Login | Login UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AUTH-F03 | EPIC-AUTH | Authentication | PIN login | PIN login UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AUTH-F04 | EPIC-AUTH | Authentication | Language onboarding | Language onboarding UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AUTH-F05 | EPIC-AUTH | Authentication | Session management | Session management UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-FARM-F01 | EPIC-FARM | Farm Management | Farm profile | Farm profile UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-FARM-F02 | EPIC-FARM | Farm Management | Farm members | Farm members UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-FARM-F03 | EPIC-FARM | Farm Management | Location dropdowns | Location dropdowns UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-FARM-F04 | EPIC-FARM | Farm Management | Veterinarian settings | Veterinarian settings UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-FARM-F05 | EPIC-FARM | Farm Management | Farm permissions | Farm permissions UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-DASH-F01 | EPIC-DASH | Dashboard | Today summary | Today summary UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-DASH-F02 | EPIC-DASH | Dashboard | Quick actions | Quick actions UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-DASH-F03 | EPIC-DASH | Dashboard | Reminder summary | Reminder summary UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-DASH-F04 | EPIC-DASH | Dashboard | Monthly performance | Monthly performance UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-DASH-F05 | EPIC-DASH | Dashboard | Pending slip banner | Pending slip banner UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-COW-F01 | EPIC-COW | Cow Management | Cow CRUD | Cow CRUD UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-COW-F02 | EPIC-COW | Cow Management | Cow profile | Cow profile UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-COW-F03 | EPIC-COW | Cow Management | Pregnancy tracking | Pregnancy tracking UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-COW-F04 | EPIC-COW | Cow Management | Calving tracking | Calving tracking UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-COW-F05 | EPIC-COW | Cow Management | Cow timeline | Cow timeline UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-CALF-F01 | EPIC-CALF | Calf Management | Calf CRUD | Calf CRUD UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-CALF-F02 | EPIC-CALF | Calf Management | Mother linking | Mother linking UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-CALF-F03 | EPIC-CALF | Calf Management | Sale/conversion status | Sale/conversion status UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-CALF-F04 | EPIC-CALF | Calf Management | Calf reminders | Calf reminders UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-CALF-F05 | EPIC-CALF | Calf Management | Growth/age display | Growth/age display UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REC-F01 | EPIC-REC | Records | Milk records | Milk records UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REC-F02 | EPIC-REC | Records | Feed records | Feed records UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REC-F03 | EPIC-REC | Records | Health records | Health records UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REC-F04 | EPIC-REC | Records | Vaccination records | Vaccination records UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REC-F05 | EPIC-REC | Records | Breeding/calving records | Breeding/calving records UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REM-F01 | EPIC-REM | Reminders | Reminder engine | Reminder engine UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REM-F02 | EPIC-REM | Reminders | Pregnancy reminders | Pregnancy reminders UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REM-F03 | EPIC-REM | Reminders | Calf care reminders | Calf care reminders UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REM-F04 | EPIC-REM | Reminders | Custom reminders | Custom reminders UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REM-F05 | EPIC-REM | Reminders | Notification integration | Notification integration UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACC-F01 | EPIC-ACC | Accounting | Milk accounting | Milk accounting UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACC-F02 | EPIC-ACC | Accounting | Settlement entry | Settlement entry UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACC-F03 | EPIC-ACC | Accounting | Expense management | Expense management UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACC-F04 | EPIC-ACC | Accounting | Profit/loss | Profit/loss UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACC-F05 | EPIC-ACC | Accounting | Financial reconciliation | Financial reconciliation UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-OCR-F01 | EPIC-OCR | OCR | Native camera/gallery | Native camera/gallery UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-OCR-F02 | EPIC-OCR | OCR | Image compression | Image compression UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-OCR-F03 | EPIC-OCR | OCR | OCR extraction | OCR extraction UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-OCR-F04 | EPIC-OCR | OCR | AI structuring | AI structuring UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-OCR-F05 | EPIC-OCR | OCR | Review and save | Review and save UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AI-F01 | EPIC-AI | AI Assistant | Chat UI | Chat UI UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AI-F02 | EPIC-AI | AI Assistant | Tool calling | Tool calling UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AI-F03 | EPIC-AI | AI Assistant | AI permissions | AI permissions UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AI-F04 | EPIC-AI | AI Assistant | Chat history | Chat history UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-AI-F05 | EPIC-AI | AI Assistant | Usage/feedback | Usage/feedback UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REP-F01 | EPIC-REP | Reports | Milk reports | Milk reports UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REP-F02 | EPIC-REP | Reports | Financial reports | Financial reports UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REP-F03 | EPIC-REP | Reports | Animal reports | Animal reports UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REP-F04 | EPIC-REP | Reports | Export/print | Export/print UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REP-F05 | EPIC-REP | Reports | Charts/filters | Charts/filters UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-NOTIF-F01 | EPIC-NOTIF | Notifications | Inbox | Inbox UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-NOTIF-F02 | EPIC-NOTIF | Notifications | Push subscription | Push subscription UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-NOTIF-F03 | EPIC-NOTIF | Notifications | Preferences | Preferences UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-NOTIF-F04 | EPIC-NOTIF | Notifications | Admin broadcasts | Admin broadcasts UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-NOTIF-F05 | EPIC-NOTIF | Notifications | Delivery logs | Delivery logs UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SET-PROF-F01 | EPIC-SET-PROF | Settings + Profile | Profile page | Profile page UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SET-PROF-F02 | EPIC-SET-PROF | Settings + Profile | Security settings | Security settings UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SET-PROF-F03 | EPIC-SET-PROF | Settings + Profile | Appearance/language | Appearance/language UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SET-PROF-F04 | EPIC-SET-PROF | Settings + Profile | AI/goal/export settings | AI/goal/export settings UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SET-PROF-F05 | EPIC-SET-PROF | Settings + Profile | Statistics | Statistics UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SUP-F01 | EPIC-SUP | Support | Help home | Help home UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SUP-F02 | EPIC-SUP | Support | FAQ/tutorials | FAQ/tutorials UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SUP-F03 | EPIC-SUP | Support | Ticket creation | Ticket creation UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SUP-F04 | EPIC-SUP | Support | Ticket replies | Ticket replies UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SUP-F05 | EPIC-SUP | Support | Support notifications | Support notifications UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACH-F01 | EPIC-ACH | Achievements | Achievement catalog | Achievement catalog UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACH-F02 | EPIC-ACH | Achievements | Score engine | Score engine UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACH-F03 | EPIC-ACH | Achievements | Leaderboard | Leaderboard UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACH-F04 | EPIC-ACH | Achievements | Badges | Badges UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ACH-F05 | EPIC-ACH | Achievements | Sharing | Sharing UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ADMIN-F01 | EPIC-ADMIN | Admin Panel | Admin dashboard | Admin dashboard UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ADMIN-F02 | EPIC-ADMIN | Admin Panel | Farm details | Farm details UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ADMIN-F03 | EPIC-ADMIN | Admin Panel | User/farm management | User/farm management UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ADMIN-F04 | EPIC-ADMIN | Admin Panel | Subscriptions/trials | Subscriptions/trials UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-ADMIN-F05 | EPIC-ADMIN | Admin Panel | Notification center | Notification center UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SEC-F01 | EPIC-SEC | Security Hardening | RLS validation | RLS validation UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SEC-F02 | EPIC-SEC | Security Hardening | API hardening | API hardening UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SEC-F03 | EPIC-SEC | Security Hardening | Storage hardening | Storage hardening UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SEC-F04 | EPIC-SEC | Security Hardening | AI/OCR security | AI/OCR security UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-SEC-F05 | EPIC-SEC | Security Hardening | Audit/monitoring | Audit/monitoring UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-PERF-F01 | EPIC-PERF | Performance Optimization | Home performance | Home performance UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-PERF-F02 | EPIC-PERF | Performance Optimization | Query optimization | Query optimization UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-PERF-F03 | EPIC-PERF | Performance Optimization | Report performance | Report performance UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-PERF-F04 | EPIC-PERF | Performance Optimization | OCR/AI latency | OCR/AI latency UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-PERF-F05 | EPIC-PERF | Performance Optimization | Bundle optimization | Bundle optimization UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REG-F01 | EPIC-REG | Bug Fixes + Regression | Regression pack | Regression pack UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REG-F02 | EPIC-REG | Bug Fixes + Regression | Defect triage | Defect triage UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REG-F03 | EPIC-REG | Bug Fixes + Regression | Financial regression | Financial regression UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REG-F04 | EPIC-REG | Bug Fixes + Regression | Mobile regression | Mobile regression UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REG-F05 | EPIC-REG | Bug Fixes + Regression | Release candidate stabilization | Release candidate stabilization UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-UAT-F01 | EPIC-UAT | UAT Support | UAT environment | UAT environment UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-UAT-F02 | EPIC-UAT | UAT Support | UAT defect support | UAT defect support UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-UAT-F03 | EPIC-UAT | UAT Support | Training support | Training support UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-UAT-F04 | EPIC-UAT | UAT Support | Pilot readiness | Pilot readiness UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-UAT-F05 | EPIC-UAT | UAT Support | Sign-off evidence | Sign-off evidence UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REL-F01 | EPIC-REL | Production Release | Release calendar | Release calendar UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REL-F02 | EPIC-REL | Production Release | Launch checklist | Launch checklist UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REL-F03 | EPIC-REL | Production Release | Migration runbook | Migration runbook UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REL-F04 | EPIC-REL | Production Release | Rollback plan | Rollback plan UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required
EPIC-REL-F05 | EPIC-REL | Production Release | Hypercare | Hypercare UI, API, validation, audit, empty/error states, Marathi/English text | Design contract, implement feature, add tests, review performance/security, update docs | API route/service/RPC, authorization, validation, audit logging | Responsive UI, loading/empty/error states, local language text, accessibility | Schema/migration/index/RLS changes if required | Functional, negative, regression, localization and mobile checks | Env vars, monitoring, feature flag and deployment checklist as required