## Releases
releaseId | releaseType | targetWindow | scope | entryCriteria | exitCriteria
R0 | Internal Alpha | After Sprint 5 | Auth, farm, cow, calf and milk records | Core workflows testable | No blocker in core data creation
R1 | MVP Beta | After Sprint 10 | Records, reminders, accounting, OCR, AI, reports | Financial/OCR/AI flows ready | Pilot farms can complete key workflows
R2 | Pilot Candidate | After Sprint 16 | Notifications, settings, support, achievements, admin, security/performance | Feature complete | Security/performance gates pass
R3 | Production Release | After Sprint 20 | Regression fixes, UAT support, release prep and launch | UAT pass >=95% | Go-live approval signed
Hotfix | Patch/Hotfix | As needed | Critical production defects only | Approved incident/defect | Fix verified and monitored

## Release Types
Type | Definition
Major Release | Broad feature release after sprint/release gate
Minor Release | Small feature or enhancement release
Patch Release | Low-risk bug fix release
Hotfix | Urgent fix for production issue with shortened approval path