## Team Options
option | roles | capacity | velocity | responsibilities | risks
Solo Founder | Full-stack engineer + PM/QA/support | 20-35 hrs/week | 15-25 points/sprint | Build highest-priority features, manual QA, deployment, support | Context switching, slower QA/security coverage
2-4 Member Startup Team | Full-stack, frontend, QA/product, part-time DevOps | 80-140 hrs/week | 45-75 points/sprint | Parallel frontend/backend/QA delivery | Need tighter backlog grooming and integration discipline
5-10 Member Product Team | PM, designer, frontend, backend, QA automation, DevOps, support | 200-350 hrs/week | 100-180 points/sprint | Feature squads, automation, security/performance in parallel | Coordination overhead and dependency management

## Capacity Plan
sprint | theme | skill | allocationWeight | notes
Sprint 0 | Project Setup | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | Security | 1 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | DevOps | 3 | Scale by selected team option and sprint risk.
Sprint 0 | Project Setup | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | Security | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 1 | Authentication + Language Selection | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | Security | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 2 | Farm Management | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | Security | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 3 | Cow Management | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | Security | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 4 | Calf Management | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | Security | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 5 | Milk Records | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | Security | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 6 | Reminders + Vaccinations | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | Security | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 7 | Accounting | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | AI/OCR | 3 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | Security | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 8 | OCR | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | AI/OCR | 3 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | Security | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 9 | AI Assistant | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | Security | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 10 | Reports | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | QA Automation | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | Security | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 11 | Notifications | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | Security | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 12 | Settings + Profile | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | Security | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 13 | Support + Achievements | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | Security | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 14 | Admin Panel | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | Security | 3 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 15 | Security Hardening | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | Security | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 16 | Performance Optimization | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | Security | 3 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 17 | Bug Fixes + Regression | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | Security | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | DevOps | 1 | Scale by selected team option and sprint risk.
Sprint 18 | UAT Support | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | Security | 3 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | DevOps | 3 | Scale by selected team option and sprint risk.
Sprint 19 | Release Preparation | Product/UAT | 1 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | Frontend | 1 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | Backend | 1 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | Supabase/PostgreSQL | 1 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | QA Automation | 3 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | Mobile PWA | 1 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | AI/OCR | 1 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | Security | 1 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | DevOps | 3 | Scale by selected team option and sprint risk.
Sprint 20 | Production Launch | Product/UAT | 1 | Scale by selected team option and sprint risk.

## Skill Requirements
Skill | Requirement
Frontend | React, Next.js App Router, Tailwind, PWA/mobile UX
Backend | Next.js API routes, Supabase service design, validation
Database | PostgreSQL, RLS, migrations, indexes, data integrity
AI/OCR | OpenAI tool-calling, OCR workflows, validation gates
QA | Functional, API, DB, security, localization, UAT automation
DevOps | CI/CD, environments, secrets, monitoring, rollback