## Risks
riskId | risk | category | probability | impact | mitigation | owner | status
DEV-RISK-001 | Financial calculation regression | Technical | Medium | Critical | Automated financial regression and settlement reconciliation | Engineering/QA | Open
DEV-RISK-002 | Cross-farm data leakage | Security | Low | Critical | RLS tests, service API guard and security review | Security/Backend | Open
DEV-RISK-003 | OCR accuracy below target | OCR | Medium | High | Golden slip set, fallback/manual review and provider monitoring | AI/OCR Engineer | Open
DEV-RISK-004 | AI hallucination or unauthorized data usage | AI | Medium | High | Function calling only, permission checks and answer verification tests | AI Engineer | Open
DEV-RISK-005 | iOS PWA instability | Technical | Medium | High | Dedicated iOS regression and session/storage QA | Frontend/QA | Open
DEV-RISK-006 | Push notification unreliability | Technical | Medium | Medium | Subscription diagnostics, fallback in-app notifications | Frontend/DevOps | Open
DEV-RISK-007 | Admin protected action misuse | Security | Low | High | Confirmation, reason, audit and role checks | Admin/Backend | Open
DEV-RISK-008 | Performance misses home/report targets | Performance | Medium | High | Caching, query indexes and budget monitoring | Engineering | Open
DEV-RISK-009 | Scope creep across settings/support/gamification | Delivery | High | Medium | MoSCoW prioritization and sprint change control | PM | Open
DEV-RISK-010 | Provider key/billing issue | Architecture | Medium | High | Provider config validation, quotas, fallback manual path | DevOps | Open
DEV-RISK-011 | UAT defects late in release | Delivery | Medium | High | Early pilot walkthroughs and sprint demos | QA/UAT Lead | Open
DEV-RISK-012 | Insufficient test data | QA | Medium | Medium | Seed scripts and golden datasets | QA/Data | Open

## Matrix
Probability | Impact | Action
High | Critical | Immediate mitigation and leadership review
Medium | Critical | Dedicated owner and sprint-level mitigation
Medium | High | Track weekly with evidence
Low | High | Monitor and verify controls