## Sprints
sprint | length | theme | objectives | epics | storyIds | storyCount | storyPoints | deliverables | dependencies | risks | definitionOfDone
Sprint 0 | 1 week setup | Project Setup | Deliver Project Setup with tested, localized and permission-safe increments. | EPIC-SETUP | DEV-US-0001, DEV-US-0002, DEV-US-0003, DEV-US-0004, DEV-US-0005, DEV-US-0006, DEV-US-0007, DEV-US-0008, DEV-US-0009, DEV-US-0010, DEV-US-0011, DEV-US-0012, DEV-US-0013, DEV-US-0014, DEV-US-0015, DEV-US-0016, DEV-US-0017, DEV-US-0018, DEV-US-0019, DEV-US-0020, DEV-US-0021, DEV-US-0022, DEV-US-0023, DEV-US-0024, DEV-US-0025 | 25 | 100 | Project Setup feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 1 | 2 weeks | Authentication + Language Selection | Deliver Authentication + Language Selection with tested, localized and permission-safe increments. | EPIC-AUTH | DEV-US-0026, DEV-US-0027, DEV-US-0028, DEV-US-0029, DEV-US-0030, DEV-US-0031, DEV-US-0032, DEV-US-0033, DEV-US-0034, DEV-US-0035, DEV-US-0036, DEV-US-0037, DEV-US-0038, DEV-US-0039, DEV-US-0040, DEV-US-0041, DEV-US-0042, DEV-US-0043, DEV-US-0044, DEV-US-0045 | 20 | 88 | Authentication + Language Selection feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 2 | 2 weeks | Farm Management | Deliver Farm Management with tested, localized and permission-safe increments. | EPIC-FARM, EPIC-DASH | DEV-US-0046, DEV-US-0047, DEV-US-0048, DEV-US-0049, DEV-US-0050, DEV-US-0051, DEV-US-0052, DEV-US-0053, DEV-US-0054, DEV-US-0055, DEV-US-0056, DEV-US-0057, DEV-US-0058, DEV-US-0059, DEV-US-0060, DEV-US-0061, DEV-US-0062, DEV-US-0063, DEV-US-0064, DEV-US-0065, DEV-US-0066, DEV-US-0067, DEV-US-0068, DEV-US-0069, DEV-US-0070 | 40 | 176 | Farm Management feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 3 | 2 weeks | Cow Management | Deliver Cow Management with tested, localized and permission-safe increments. | EPIC-COW | DEV-US-0086, DEV-US-0087, DEV-US-0088, DEV-US-0089, DEV-US-0090, DEV-US-0091, DEV-US-0092, DEV-US-0093, DEV-US-0094, DEV-US-0095, DEV-US-0096, DEV-US-0097, DEV-US-0098, DEV-US-0099, DEV-US-0100, DEV-US-0101, DEV-US-0102, DEV-US-0103, DEV-US-0104, DEV-US-0105 | 20 | 88 | Cow Management feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 4 | 2 weeks | Calf Management | Deliver Calf Management with tested, localized and permission-safe increments. | EPIC-CALF | DEV-US-0106, DEV-US-0107, DEV-US-0108, DEV-US-0109, DEV-US-0110, DEV-US-0111, DEV-US-0112, DEV-US-0113, DEV-US-0114, DEV-US-0115, DEV-US-0116, DEV-US-0117, DEV-US-0118, DEV-US-0119, DEV-US-0120, DEV-US-0121, DEV-US-0122, DEV-US-0123, DEV-US-0124, DEV-US-0125 | 20 | 88 | Calf Management feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 5 | 2 weeks | Milk Records | Deliver Milk Records with tested, localized and permission-safe increments. | EPIC-REC | DEV-US-0126, DEV-US-0127, DEV-US-0128, DEV-US-0129, DEV-US-0130, DEV-US-0131, DEV-US-0132, DEV-US-0133, DEV-US-0134, DEV-US-0135, DEV-US-0136, DEV-US-0137, DEV-US-0138, DEV-US-0139, DEV-US-0140, DEV-US-0141, DEV-US-0142, DEV-US-0143, DEV-US-0144, DEV-US-0145 | 20 | 88 | Milk Records feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 6 | 2 weeks | Reminders + Vaccinations | Deliver Reminders + Vaccinations with tested, localized and permission-safe increments. | EPIC-REM | DEV-US-0146, DEV-US-0147, DEV-US-0148, DEV-US-0149, DEV-US-0150, DEV-US-0151, DEV-US-0152, DEV-US-0153, DEV-US-0154, DEV-US-0155, DEV-US-0156, DEV-US-0157, DEV-US-0158, DEV-US-0159, DEV-US-0160, DEV-US-0161, DEV-US-0162, DEV-US-0163, DEV-US-0164, DEV-US-0165 | 20 | 88 | Reminders + Vaccinations feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 7 | 2 weeks | Accounting | Deliver Accounting with tested, localized and permission-safe increments. | EPIC-ACC | DEV-US-0166, DEV-US-0167, DEV-US-0168, DEV-US-0169, DEV-US-0170, DEV-US-0171, DEV-US-0172, DEV-US-0173, DEV-US-0174, DEV-US-0175, DEV-US-0176, DEV-US-0177, DEV-US-0178, DEV-US-0179, DEV-US-0180, DEV-US-0181, DEV-US-0182, DEV-US-0183, DEV-US-0184, DEV-US-0185 | 20 | 148 | Accounting feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 8 | 2 weeks | OCR | Deliver OCR with tested, localized and permission-safe increments. | EPIC-OCR | DEV-US-0186, DEV-US-0187, DEV-US-0188, DEV-US-0189, DEV-US-0190, DEV-US-0191, DEV-US-0192, DEV-US-0193, DEV-US-0194, DEV-US-0195, DEV-US-0196, DEV-US-0197, DEV-US-0198, DEV-US-0199, DEV-US-0200, DEV-US-0201, DEV-US-0202, DEV-US-0203, DEV-US-0204, DEV-US-0205, DEV-US-0206, DEV-US-0207, DEV-US-0208, DEV-US-0209, DEV-US-0210 | 25 | 175 | OCR feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 9 | 2 weeks | AI Assistant | Deliver AI Assistant with tested, localized and permission-safe increments. | EPIC-AI | DEV-US-0211, DEV-US-0212, DEV-US-0213, DEV-US-0214, DEV-US-0215, DEV-US-0216, DEV-US-0217, DEV-US-0218, DEV-US-0219, DEV-US-0220, DEV-US-0221, DEV-US-0222, DEV-US-0223, DEV-US-0224, DEV-US-0225, DEV-US-0226, DEV-US-0227, DEV-US-0228, DEV-US-0229, DEV-US-0230, DEV-US-0231, DEV-US-0232, DEV-US-0233, DEV-US-0234, DEV-US-0235 | 25 | 100 | AI Assistant feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 10 | 2 weeks | Reports | Deliver Reports with tested, localized and permission-safe increments. | EPIC-REP | DEV-US-0236, DEV-US-0237, DEV-US-0238, DEV-US-0239, DEV-US-0240, DEV-US-0241, DEV-US-0242, DEV-US-0243, DEV-US-0244, DEV-US-0245, DEV-US-0246, DEV-US-0247, DEV-US-0248, DEV-US-0249, DEV-US-0250, DEV-US-0251, DEV-US-0252, DEV-US-0253, DEV-US-0254, DEV-US-0255 | 20 | 88 | Reports feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 11 | 2 weeks | Notifications | Deliver Notifications with tested, localized and permission-safe increments. | EPIC-NOTIF | DEV-US-0256, DEV-US-0257, DEV-US-0258, DEV-US-0259, DEV-US-0260, DEV-US-0261, DEV-US-0262, DEV-US-0263, DEV-US-0264, DEV-US-0265, DEV-US-0266, DEV-US-0267, DEV-US-0268, DEV-US-0269, DEV-US-0270, DEV-US-0271, DEV-US-0272, DEV-US-0273, DEV-US-0274, DEV-US-0275, DEV-US-0276, DEV-US-0277, DEV-US-0278, DEV-US-0279, DEV-US-0280 | 25 | 100 | Notifications feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 12 | 2 weeks | Settings + Profile | Deliver Settings + Profile with tested, localized and permission-safe increments. | EPIC-SET-PROF | DEV-US-0281, DEV-US-0282, DEV-US-0283, DEV-US-0284, DEV-US-0285, DEV-US-0286, DEV-US-0287, DEV-US-0288, DEV-US-0289, DEV-US-0290, DEV-US-0291, DEV-US-0292, DEV-US-0293, DEV-US-0294, DEV-US-0295, DEV-US-0296, DEV-US-0297, DEV-US-0298, DEV-US-0299, DEV-US-0300 | 20 | 88 | Settings + Profile feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 13 | 2 weeks | Support + Achievements | Deliver Support + Achievements with tested, localized and permission-safe increments. | EPIC-SUP, EPIC-ACH | DEV-US-0301, DEV-US-0302, DEV-US-0303, DEV-US-0304, DEV-US-0305, DEV-US-0306, DEV-US-0307, DEV-US-0308, DEV-US-0309, DEV-US-0310, DEV-US-0311, DEV-US-0312, DEV-US-0313, DEV-US-0314, DEV-US-0315, DEV-US-0316, DEV-US-0317, DEV-US-0318, DEV-US-0319, DEV-US-0320, DEV-US-0321, DEV-US-0322, DEV-US-0323, DEV-US-0324, DEV-US-0325 | 40 | 176 | Support + Achievements feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 14 | 2 weeks | Admin Panel | Deliver Admin Panel with tested, localized and permission-safe increments. | EPIC-ADMIN | DEV-US-0341, DEV-US-0342, DEV-US-0343, DEV-US-0344, DEV-US-0345, DEV-US-0346, DEV-US-0347, DEV-US-0348, DEV-US-0349, DEV-US-0350, DEV-US-0351, DEV-US-0352, DEV-US-0353, DEV-US-0354, DEV-US-0355, DEV-US-0356, DEV-US-0357, DEV-US-0358, DEV-US-0359, DEV-US-0360, DEV-US-0361, DEV-US-0362, DEV-US-0363, DEV-US-0364, DEV-US-0365 | 25 | 175 | Admin Panel feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 15 | 2 weeks | Security Hardening | Deliver Security Hardening with tested, localized and permission-safe increments. | EPIC-SEC | DEV-US-0366, DEV-US-0367, DEV-US-0368, DEV-US-0369, DEV-US-0370, DEV-US-0371, DEV-US-0372, DEV-US-0373, DEV-US-0374, DEV-US-0375, DEV-US-0376, DEV-US-0377, DEV-US-0378, DEV-US-0379, DEV-US-0380, DEV-US-0381, DEV-US-0382, DEV-US-0383, DEV-US-0384, DEV-US-0385, DEV-US-0386, DEV-US-0387, DEV-US-0388, DEV-US-0389, DEV-US-0390 | 25 | 175 | Security Hardening feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 16 | 2 weeks | Performance Optimization | Deliver Performance Optimization with tested, localized and permission-safe increments. | EPIC-PERF | DEV-US-0391, DEV-US-0392, DEV-US-0393, DEV-US-0394, DEV-US-0395, DEV-US-0396, DEV-US-0397, DEV-US-0398, DEV-US-0399, DEV-US-0400, DEV-US-0401, DEV-US-0402, DEV-US-0403, DEV-US-0404, DEV-US-0405, DEV-US-0406, DEV-US-0407, DEV-US-0408, DEV-US-0409, DEV-US-0410, DEV-US-0411, DEV-US-0412, DEV-US-0413, DEV-US-0414, DEV-US-0415 | 25 | 100 | Performance Optimization feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 17 | 2 weeks | Bug Fixes + Regression | Deliver Bug Fixes + Regression with tested, localized and permission-safe increments. | EPIC-REG | DEV-US-0416, DEV-US-0417, DEV-US-0418, DEV-US-0419, DEV-US-0420, DEV-US-0421, DEV-US-0422, DEV-US-0423, DEV-US-0424, DEV-US-0425, DEV-US-0426, DEV-US-0427, DEV-US-0428, DEV-US-0429, DEV-US-0430, DEV-US-0431, DEV-US-0432, DEV-US-0433, DEV-US-0434, DEV-US-0435 | 20 | 88 | Bug Fixes + Regression feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 18 | 2 weeks | UAT Support | Deliver UAT Support with tested, localized and permission-safe increments. | EPIC-UAT | DEV-US-0436, DEV-US-0437, DEV-US-0438, DEV-US-0439, DEV-US-0440, DEV-US-0441, DEV-US-0442, DEV-US-0443, DEV-US-0444, DEV-US-0445, DEV-US-0446, DEV-US-0447, DEV-US-0448, DEV-US-0449, DEV-US-0450, DEV-US-0451, DEV-US-0452, DEV-US-0453, DEV-US-0454, DEV-US-0455 | 20 | 88 | UAT Support feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 19 | 2 weeks | Release Preparation | Deliver Release Preparation with tested, localized and permission-safe increments. | EPIC-REL, EPIC-REG | DEV-US-0416, DEV-US-0417, DEV-US-0418, DEV-US-0419, DEV-US-0420, DEV-US-0421, DEV-US-0422, DEV-US-0423, DEV-US-0424, DEV-US-0425, DEV-US-0426, DEV-US-0427, DEV-US-0428, DEV-US-0429, DEV-US-0430, DEV-US-0431, DEV-US-0432, DEV-US-0433 | 18 | 80 | Release Preparation feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.
Sprint 20 | 2 weeks | Production Launch | Deliver Production Launch with tested, localized and permission-safe increments. | EPIC-REL | DEV-US-0474, DEV-US-0475, DEV-US-0476, DEV-US-0477, DEV-US-0478, DEV-US-0479, DEV-US-0480 | 7 | 27 | Production Launch feature increment, tests, docs and release notes. | Previous sprint deliverables; environment and data readiness. | Scope creep, integration defects, mobile regressions, security/RLS issues. | Code reviewed, tests pass, QA accepted, no Critical/High defects, Marathi/English verified, audit/security requirements met.

## Sprint Story Map
storyId | epicId | featureId | title | priority | storyPoints | estimatedHours | targetSprint | status
DEV-US-0001 | EPIC-SETUP | EPIC-SETUP-F01 | Backend: Repository standards | Medium | 5 | 30 | 0 | Backlog
DEV-US-0002 | EPIC-SETUP | EPIC-SETUP-F01 | Frontend: Repository standards | Medium | 5 | 30 | 0 | Backlog
DEV-US-0003 | EPIC-SETUP | EPIC-SETUP-F01 | Database: Repository standards | Medium | 3 | 18 | 0 | Backlog
DEV-US-0004 | EPIC-SETUP | EPIC-SETUP-F01 | QA: Repository standards | Medium | 3 | 18 | 0 | Backlog
DEV-US-0005 | EPIC-SETUP | EPIC-SETUP-F01 | DevOps: Repository standards | High | 4 | 24 | 0 | Backlog
DEV-US-0006 | EPIC-SETUP | EPIC-SETUP-F02 | Backend: Environment configuration | Medium | 5 | 30 | 0 | Backlog
DEV-US-0007 | EPIC-SETUP | EPIC-SETUP-F02 | Frontend: Environment configuration | Medium | 5 | 30 | 0 | Backlog
DEV-US-0008 | EPIC-SETUP | EPIC-SETUP-F02 | Database: Environment configuration | Medium | 3 | 18 | 0 | Backlog
DEV-US-0009 | EPIC-SETUP | EPIC-SETUP-F02 | QA: Environment configuration | Medium | 3 | 18 | 0 | Backlog
DEV-US-0010 | EPIC-SETUP | EPIC-SETUP-F02 | DevOps: Environment configuration | High | 4 | 24 | 0 | Backlog
DEV-US-0011 | EPIC-SETUP | EPIC-SETUP-F03 | Backend: CI/CD pipeline | Medium | 5 | 30 | 0 | Backlog
DEV-US-0012 | EPIC-SETUP | EPIC-SETUP-F03 | Frontend: CI/CD pipeline | Medium | 5 | 30 | 0 | Backlog
DEV-US-0013 | EPIC-SETUP | EPIC-SETUP-F03 | Database: CI/CD pipeline | Medium | 3 | 18 | 0 | Backlog
DEV-US-0014 | EPIC-SETUP | EPIC-SETUP-F03 | QA: CI/CD pipeline | Medium | 3 | 18 | 0 | Backlog
DEV-US-0015 | EPIC-SETUP | EPIC-SETUP-F03 | DevOps: CI/CD pipeline | High | 4 | 24 | 0 | Backlog
DEV-US-0016 | EPIC-SETUP | EPIC-SETUP-F04 | Backend: Coding conventions | Medium | 5 | 30 | 0 | Backlog
DEV-US-0017 | EPIC-SETUP | EPIC-SETUP-F04 | Frontend: Coding conventions | Medium | 5 | 30 | 0 | Backlog
DEV-US-0018 | EPIC-SETUP | EPIC-SETUP-F04 | Database: Coding conventions | Medium | 3 | 18 | 0 | Backlog
DEV-US-0019 | EPIC-SETUP | EPIC-SETUP-F04 | QA: Coding conventions | Medium | 3 | 18 | 0 | Backlog
DEV-US-0020 | EPIC-SETUP | EPIC-SETUP-F04 | DevOps: Coding conventions | High | 4 | 24 | 0 | Backlog
DEV-US-0021 | EPIC-SETUP | EPIC-SETUP-F05 | Backend: Observability baseline | Medium | 5 | 30 | 0 | Backlog
DEV-US-0022 | EPIC-SETUP | EPIC-SETUP-F05 | Frontend: Observability baseline | Medium | 5 | 30 | 0 | Backlog
DEV-US-0023 | EPIC-SETUP | EPIC-SETUP-F05 | Database: Observability baseline | Medium | 3 | 18 | 0 | Backlog
DEV-US-0024 | EPIC-SETUP | EPIC-SETUP-F05 | QA: Observability baseline | Medium | 3 | 18 | 0 | Backlog
DEV-US-0025 | EPIC-SETUP | EPIC-SETUP-F05 | DevOps: Observability baseline | High | 4 | 24 | 0 | Backlog
DEV-US-0026 | EPIC-AUTH | EPIC-AUTH-F01 | Backend: Signup | High | 5 | 30 | 1 | Backlog
DEV-US-0027 | EPIC-AUTH | EPIC-AUTH-F01 | Frontend: Signup | High | 5 | 30 | 1 | Backlog
DEV-US-0028 | EPIC-AUTH | EPIC-AUTH-F01 | Database: Signup | High | 3 | 18 | 1 | Backlog
DEV-US-0029 | EPIC-AUTH | EPIC-AUTH-F01 | QA: Signup | High | 3 | 18 | 1 | Backlog
DEV-US-0030 | EPIC-AUTH | EPIC-AUTH-F02 | Backend: Login | High | 7 | 42 | 1 | Backlog
DEV-US-0031 | EPIC-AUTH | EPIC-AUTH-F02 | Frontend: Login | High | 5 | 30 | 1 | Backlog
DEV-US-0032 | EPIC-AUTH | EPIC-AUTH-F02 | Database: Login | High | 3 | 18 | 1 | Backlog
DEV-US-0033 | EPIC-AUTH | EPIC-AUTH-F02 | QA: Login | High | 3 | 18 | 1 | Backlog
DEV-US-0034 | EPIC-AUTH | EPIC-AUTH-F03 | Backend: PIN login | High | 5 | 30 | 1 | Backlog
DEV-US-0035 | EPIC-AUTH | EPIC-AUTH-F03 | Frontend: PIN login | High | 7 | 42 | 1 | Backlog
DEV-US-0036 | EPIC-AUTH | EPIC-AUTH-F03 | Database: PIN login | High | 3 | 18 | 1 | Backlog
DEV-US-0037 | EPIC-AUTH | EPIC-AUTH-F03 | QA: PIN login | High | 3 | 18 | 1 | Backlog
DEV-US-0038 | EPIC-AUTH | EPIC-AUTH-F04 | Backend: Language onboarding | High | 5 | 30 | 1 | Backlog
DEV-US-0039 | EPIC-AUTH | EPIC-AUTH-F04 | Frontend: Language onboarding | High | 5 | 30 | 1 | Backlog
DEV-US-0040 | EPIC-AUTH | EPIC-AUTH-F04 | Database: Language onboarding | High | 5 | 30 | 1 | Backlog
DEV-US-0041 | EPIC-AUTH | EPIC-AUTH-F04 | QA: Language onboarding | High | 3 | 18 | 1 | Backlog
DEV-US-0042 | EPIC-AUTH | EPIC-AUTH-F05 | Backend: Session management | High | 5 | 30 | 1 | Backlog
DEV-US-0043 | EPIC-AUTH | EPIC-AUTH-F05 | Frontend: Session management | High | 5 | 30 | 1 | Backlog
DEV-US-0044 | EPIC-AUTH | EPIC-AUTH-F05 | Database: Session management | High | 3 | 18 | 1 | Backlog
DEV-US-0045 | EPIC-AUTH | EPIC-AUTH-F05 | QA: Session management | High | 5 | 30 | 1 | Backlog
DEV-US-0046 | EPIC-FARM | EPIC-FARM-F01 | Backend: Farm profile | Medium | 5 | 30 | 2 | Backlog
DEV-US-0047 | EPIC-FARM | EPIC-FARM-F01 | Frontend: Farm profile | Medium | 5 | 30 | 2 | Backlog
DEV-US-0048 | EPIC-FARM | EPIC-FARM-F01 | Database: Farm profile | Medium | 3 | 18 | 2 | Backlog
DEV-US-0049 | EPIC-FARM | EPIC-FARM-F01 | QA: Farm profile | Medium | 3 | 18 | 2 | Backlog
DEV-US-0050 | EPIC-FARM | EPIC-FARM-F02 | Backend: Farm members | Medium | 7 | 42 | 2 | Backlog
DEV-US-0051 | EPIC-FARM | EPIC-FARM-F02 | Frontend: Farm members | Medium | 5 | 30 | 2 | Backlog
DEV-US-0052 | EPIC-FARM | EPIC-FARM-F02 | Database: Farm members | Medium | 3 | 18 | 2 | Backlog
DEV-US-0053 | EPIC-FARM | EPIC-FARM-F02 | QA: Farm members | Medium | 3 | 18 | 2 | Backlog
DEV-US-0054 | EPIC-FARM | EPIC-FARM-F03 | Backend: Location dropdowns | Medium | 5 | 30 | 2 | Backlog
DEV-US-0055 | EPIC-FARM | EPIC-FARM-F03 | Frontend: Location dropdowns | Medium | 7 | 42 | 2 | Backlog
DEV-US-0056 | EPIC-FARM | EPIC-FARM-F03 | Database: Location dropdowns | Medium | 3 | 18 | 2 | Backlog
DEV-US-0057 | EPIC-FARM | EPIC-FARM-F03 | QA: Location dropdowns | Medium | 3 | 18 | 2 | Backlog
DEV-US-0058 | EPIC-FARM | EPIC-FARM-F04 | Backend: Veterinarian settings | Medium | 5 | 30 | 2 | Backlog
DEV-US-0059 | EPIC-FARM | EPIC-FARM-F04 | Frontend: Veterinarian settings | Medium | 5 | 30 | 2 | Backlog
DEV-US-0060 | EPIC-FARM | EPIC-FARM-F04 | Database: Veterinarian settings | Medium | 5 | 30 | 2 | Backlog
DEV-US-0061 | EPIC-FARM | EPIC-FARM-F04 | QA: Veterinarian settings | Medium | 3 | 18 | 2 | Backlog
DEV-US-0062 | EPIC-FARM | EPIC-FARM-F05 | Backend: Farm permissions | Medium | 5 | 30 | 2 | Backlog
DEV-US-0063 | EPIC-FARM | EPIC-FARM-F05 | Frontend: Farm permissions | Medium | 5 | 30 | 2 | Backlog
DEV-US-0064 | EPIC-FARM | EPIC-FARM-F05 | Database: Farm permissions | Medium | 3 | 18 | 2 | Backlog
DEV-US-0065 | EPIC-FARM | EPIC-FARM-F05 | QA: Farm permissions | Medium | 5 | 30 | 2 | Backlog
DEV-US-0066 | EPIC-DASH | EPIC-DASH-F01 | Backend: Today summary | Medium | 5 | 30 | 2 | Backlog
DEV-US-0067 | EPIC-DASH | EPIC-DASH-F01 | Frontend: Today summary | Medium | 5 | 30 | 2 | Backlog
DEV-US-0068 | EPIC-DASH | EPIC-DASH-F01 | Database: Today summary | Medium | 3 | 18 | 2 | Backlog
DEV-US-0069 | EPIC-DASH | EPIC-DASH-F01 | QA: Today summary | Medium | 3 | 18 | 2 | Backlog
DEV-US-0070 | EPIC-DASH | EPIC-DASH-F02 | Backend: Quick actions | Medium | 7 | 42 | 2 | Backlog
DEV-US-0071 | EPIC-DASH | EPIC-DASH-F02 | Frontend: Quick actions | Medium | 5 | 30 | 2 | Backlog
DEV-US-0072 | EPIC-DASH | EPIC-DASH-F02 | Database: Quick actions | Medium | 3 | 18 | 2 | Backlog
DEV-US-0073 | EPIC-DASH | EPIC-DASH-F02 | QA: Quick actions | Medium | 3 | 18 | 2 | Backlog
DEV-US-0074 | EPIC-DASH | EPIC-DASH-F03 | Backend: Reminder summary | Medium | 5 | 30 | 2 | Backlog
DEV-US-0075 | EPIC-DASH | EPIC-DASH-F03 | Frontend: Reminder summary | Medium | 7 | 42 | 2 | Backlog
DEV-US-0076 | EPIC-DASH | EPIC-DASH-F03 | Database: Reminder summary | Medium | 3 | 18 | 2 | Backlog
DEV-US-0077 | EPIC-DASH | EPIC-DASH-F03 | QA: Reminder summary | Medium | 3 | 18 | 2 | Backlog
DEV-US-0078 | EPIC-DASH | EPIC-DASH-F04 | Backend: Monthly performance | Medium | 5 | 30 | 2 | Backlog
DEV-US-0079 | EPIC-DASH | EPIC-DASH-F04 | Frontend: Monthly performance | Medium | 5 | 30 | 2 | Backlog
DEV-US-0080 | EPIC-DASH | EPIC-DASH-F04 | Database: Monthly performance | Medium | 5 | 30 | 2 | Backlog
DEV-US-0081 | EPIC-DASH | EPIC-DASH-F04 | QA: Monthly performance | Medium | 3 | 18 | 2 | Backlog
DEV-US-0082 | EPIC-DASH | EPIC-DASH-F05 | Backend: Pending slip banner | Medium | 5 | 30 | 2 | Backlog
DEV-US-0083 | EPIC-DASH | EPIC-DASH-F05 | Frontend: Pending slip banner | Medium | 5 | 30 | 2 | Backlog
DEV-US-0084 | EPIC-DASH | EPIC-DASH-F05 | Database: Pending slip banner | Medium | 3 | 18 | 2 | Backlog
DEV-US-0085 | EPIC-DASH | EPIC-DASH-F05 | QA: Pending slip banner | Medium | 5 | 30 | 2 | Backlog
DEV-US-0086 | EPIC-COW | EPIC-COW-F01 | Backend: Cow CRUD | Medium | 5 | 30 | 3 | Backlog
DEV-US-0087 | EPIC-COW | EPIC-COW-F01 | Frontend: Cow CRUD | Medium | 5 | 30 | 3 | Backlog
DEV-US-0088 | EPIC-COW | EPIC-COW-F01 | Database: Cow CRUD | Medium | 3 | 18 | 3 | Backlog
DEV-US-0089 | EPIC-COW | EPIC-COW-F01 | QA: Cow CRUD | Medium | 3 | 18 | 3 | Backlog
DEV-US-0090 | EPIC-COW | EPIC-COW-F02 | Backend: Cow profile | Medium | 7 | 42 | 3 | Backlog
DEV-US-0091 | EPIC-COW | EPIC-COW-F02 | Frontend: Cow profile | Medium | 5 | 30 | 3 | Backlog
DEV-US-0092 | EPIC-COW | EPIC-COW-F02 | Database: Cow profile | Medium | 3 | 18 | 3 | Backlog
DEV-US-0093 | EPIC-COW | EPIC-COW-F02 | QA: Cow profile | Medium | 3 | 18 | 3 | Backlog
DEV-US-0094 | EPIC-COW | EPIC-COW-F03 | Backend: Pregnancy tracking | Medium | 5 | 30 | 3 | Backlog
DEV-US-0095 | EPIC-COW | EPIC-COW-F03 | Frontend: Pregnancy tracking | Medium | 7 | 42 | 3 | Backlog
DEV-US-0096 | EPIC-COW | EPIC-COW-F03 | Database: Pregnancy tracking | Medium | 3 | 18 | 3 | Backlog
DEV-US-0097 | EPIC-COW | EPIC-COW-F03 | QA: Pregnancy tracking | Medium | 3 | 18 | 3 | Backlog
DEV-US-0098 | EPIC-COW | EPIC-COW-F04 | Backend: Calving tracking | Medium | 5 | 30 | 3 | Backlog
DEV-US-0099 | EPIC-COW | EPIC-COW-F04 | Frontend: Calving tracking | Medium | 5 | 30 | 3 | Backlog
DEV-US-0100 | EPIC-COW | EPIC-COW-F04 | Database: Calving tracking | Medium | 5 | 30 | 3 | Backlog
DEV-US-0101 | EPIC-COW | EPIC-COW-F04 | QA: Calving tracking | Medium | 3 | 18 | 3 | Backlog
DEV-US-0102 | EPIC-COW | EPIC-COW-F05 | Backend: Cow timeline | Medium | 5 | 30 | 3 | Backlog
DEV-US-0103 | EPIC-COW | EPIC-COW-F05 | Frontend: Cow timeline | Medium | 5 | 30 | 3 | Backlog
DEV-US-0104 | EPIC-COW | EPIC-COW-F05 | Database: Cow timeline | Medium | 3 | 18 | 3 | Backlog
DEV-US-0105 | EPIC-COW | EPIC-COW-F05 | QA: Cow timeline | Medium | 5 | 30 | 3 | Backlog
DEV-US-0106 | EPIC-CALF | EPIC-CALF-F01 | Backend: Calf CRUD | Medium | 5 | 30 | 4 | Backlog
DEV-US-0107 | EPIC-CALF | EPIC-CALF-F01 | Frontend: Calf CRUD | Medium | 5 | 30 | 4 | Backlog
DEV-US-0108 | EPIC-CALF | EPIC-CALF-F01 | Database: Calf CRUD | Medium | 3 | 18 | 4 | Backlog
DEV-US-0109 | EPIC-CALF | EPIC-CALF-F01 | QA: Calf CRUD | Medium | 3 | 18 | 4 | Backlog
DEV-US-0110 | EPIC-CALF | EPIC-CALF-F02 | Backend: Mother linking | Medium | 7 | 42 | 4 | Backlog
DEV-US-0111 | EPIC-CALF | EPIC-CALF-F02 | Frontend: Mother linking | Medium | 5 | 30 | 4 | Backlog
DEV-US-0112 | EPIC-CALF | EPIC-CALF-F02 | Database: Mother linking | Medium | 3 | 18 | 4 | Backlog
DEV-US-0113 | EPIC-CALF | EPIC-CALF-F02 | QA: Mother linking | Medium | 3 | 18 | 4 | Backlog
DEV-US-0114 | EPIC-CALF | EPIC-CALF-F03 | Backend: Sale/conversion status | Medium | 5 | 30 | 4 | Backlog
DEV-US-0115 | EPIC-CALF | EPIC-CALF-F03 | Frontend: Sale/conversion status | Medium | 7 | 42 | 4 | Backlog
DEV-US-0116 | EPIC-CALF | EPIC-CALF-F03 | Database: Sale/conversion status | Medium | 3 | 18 | 4 | Backlog
DEV-US-0117 | EPIC-CALF | EPIC-CALF-F03 | QA: Sale/conversion status | Medium | 3 | 18 | 4 | Backlog
DEV-US-0118 | EPIC-CALF | EPIC-CALF-F04 | Backend: Calf reminders | Medium | 5 | 30 | 4 | Backlog
DEV-US-0119 | EPIC-CALF | EPIC-CALF-F04 | Frontend: Calf reminders | Medium | 5 | 30 | 4 | Backlog
DEV-US-0120 | EPIC-CALF | EPIC-CALF-F04 | Database: Calf reminders | Medium | 5 | 30 | 4 | Backlog
DEV-US-0121 | EPIC-CALF | EPIC-CALF-F04 | QA: Calf reminders | Medium | 3 | 18 | 4 | Backlog
DEV-US-0122 | EPIC-CALF | EPIC-CALF-F05 | Backend: Growth/age display | Medium | 5 | 30 | 4 | Backlog
DEV-US-0123 | EPIC-CALF | EPIC-CALF-F05 | Frontend: Growth/age display | Medium | 5 | 30 | 4 | Backlog
DEV-US-0124 | EPIC-CALF | EPIC-CALF-F05 | Database: Growth/age display | Medium | 3 | 18 | 4 | Backlog
DEV-US-0125 | EPIC-CALF | EPIC-CALF-F05 | QA: Growth/age display | Medium | 5 | 30 | 4 | Backlog
DEV-US-0126 | EPIC-REC | EPIC-REC-F01 | Backend: Milk records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0127 | EPIC-REC | EPIC-REC-F01 | Frontend: Milk records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0128 | EPIC-REC | EPIC-REC-F01 | Database: Milk records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0129 | EPIC-REC | EPIC-REC-F01 | QA: Milk records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0130 | EPIC-REC | EPIC-REC-F02 | Backend: Feed records | Medium | 7 | 42 | 5 | Backlog
DEV-US-0131 | EPIC-REC | EPIC-REC-F02 | Frontend: Feed records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0132 | EPIC-REC | EPIC-REC-F02 | Database: Feed records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0133 | EPIC-REC | EPIC-REC-F02 | QA: Feed records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0134 | EPIC-REC | EPIC-REC-F03 | Backend: Health records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0135 | EPIC-REC | EPIC-REC-F03 | Frontend: Health records | Medium | 7 | 42 | 5 | Backlog
DEV-US-0136 | EPIC-REC | EPIC-REC-F03 | Database: Health records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0137 | EPIC-REC | EPIC-REC-F03 | QA: Health records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0138 | EPIC-REC | EPIC-REC-F04 | Backend: Vaccination records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0139 | EPIC-REC | EPIC-REC-F04 | Frontend: Vaccination records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0140 | EPIC-REC | EPIC-REC-F04 | Database: Vaccination records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0141 | EPIC-REC | EPIC-REC-F04 | QA: Vaccination records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0142 | EPIC-REC | EPIC-REC-F05 | Backend: Breeding/calving records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0143 | EPIC-REC | EPIC-REC-F05 | Frontend: Breeding/calving records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0144 | EPIC-REC | EPIC-REC-F05 | Database: Breeding/calving records | Medium | 3 | 18 | 5 | Backlog
DEV-US-0145 | EPIC-REC | EPIC-REC-F05 | QA: Breeding/calving records | Medium | 5 | 30 | 5 | Backlog
DEV-US-0146 | EPIC-REM | EPIC-REM-F01 | Backend: Reminder engine | Medium | 5 | 30 | 6 | Backlog
DEV-US-0147 | EPIC-REM | EPIC-REM-F01 | Frontend: Reminder engine | Medium | 5 | 30 | 6 | Backlog
DEV-US-0148 | EPIC-REM | EPIC-REM-F01 | Database: Reminder engine | Medium | 3 | 18 | 6 | Backlog
DEV-US-0149 | EPIC-REM | EPIC-REM-F01 | QA: Reminder engine | Medium | 3 | 18 | 6 | Backlog
DEV-US-0150 | EPIC-REM | EPIC-REM-F02 | Backend: Pregnancy reminders | Medium | 7 | 42 | 6 | Backlog
DEV-US-0151 | EPIC-REM | EPIC-REM-F02 | Frontend: Pregnancy reminders | Medium | 5 | 30 | 6 | Backlog
DEV-US-0152 | EPIC-REM | EPIC-REM-F02 | Database: Pregnancy reminders | Medium | 3 | 18 | 6 | Backlog
DEV-US-0153 | EPIC-REM | EPIC-REM-F02 | QA: Pregnancy reminders | Medium | 3 | 18 | 6 | Backlog
DEV-US-0154 | EPIC-REM | EPIC-REM-F03 | Backend: Calf care reminders | Medium | 5 | 30 | 6 | Backlog
DEV-US-0155 | EPIC-REM | EPIC-REM-F03 | Frontend: Calf care reminders | Medium | 7 | 42 | 6 | Backlog
DEV-US-0156 | EPIC-REM | EPIC-REM-F03 | Database: Calf care reminders | Medium | 3 | 18 | 6 | Backlog
DEV-US-0157 | EPIC-REM | EPIC-REM-F03 | QA: Calf care reminders | Medium | 3 | 18 | 6 | Backlog
DEV-US-0158 | EPIC-REM | EPIC-REM-F04 | Backend: Custom reminders | Medium | 5 | 30 | 6 | Backlog
DEV-US-0159 | EPIC-REM | EPIC-REM-F04 | Frontend: Custom reminders | Medium | 5 | 30 | 6 | Backlog
DEV-US-0160 | EPIC-REM | EPIC-REM-F04 | Database: Custom reminders | Medium | 5 | 30 | 6 | Backlog
DEV-US-0161 | EPIC-REM | EPIC-REM-F04 | QA: Custom reminders | Medium | 3 | 18 | 6 | Backlog
DEV-US-0162 | EPIC-REM | EPIC-REM-F05 | Backend: Notification integration | Medium | 5 | 30 | 6 | Backlog
DEV-US-0163 | EPIC-REM | EPIC-REM-F05 | Frontend: Notification integration | Medium | 5 | 30 | 6 | Backlog
DEV-US-0164 | EPIC-REM | EPIC-REM-F05 | Database: Notification integration | Medium | 3 | 18 | 6 | Backlog
DEV-US-0165 | EPIC-REM | EPIC-REM-F05 | QA: Notification integration | Medium | 5 | 30 | 6 | Backlog
DEV-US-0166 | EPIC-ACC | EPIC-ACC-F01 | Backend: Milk accounting | High | 8 | 48 | 7 | Backlog
DEV-US-0167 | EPIC-ACC | EPIC-ACC-F01 | Frontend: Milk accounting | High | 8 | 48 | 7 | Backlog
DEV-US-0168 | EPIC-ACC | EPIC-ACC-F01 | Database: Milk accounting | High | 6 | 36 | 7 | Backlog
DEV-US-0169 | EPIC-ACC | EPIC-ACC-F01 | QA: Milk accounting | High | 6 | 36 | 7 | Backlog
DEV-US-0170 | EPIC-ACC | EPIC-ACC-F02 | Backend: Settlement entry | High | 10 | 60 | 7 | Backlog
DEV-US-0171 | EPIC-ACC | EPIC-ACC-F02 | Frontend: Settlement entry | High | 8 | 48 | 7 | Backlog
DEV-US-0172 | EPIC-ACC | EPIC-ACC-F02 | Database: Settlement entry | High | 6 | 36 | 7 | Backlog
DEV-US-0173 | EPIC-ACC | EPIC-ACC-F02 | QA: Settlement entry | High | 6 | 36 | 7 | Backlog
DEV-US-0174 | EPIC-ACC | EPIC-ACC-F03 | Backend: Expense management | High | 8 | 48 | 7 | Backlog
DEV-US-0175 | EPIC-ACC | EPIC-ACC-F03 | Frontend: Expense management | High | 10 | 60 | 7 | Backlog
DEV-US-0176 | EPIC-ACC | EPIC-ACC-F03 | Database: Expense management | High | 6 | 36 | 7 | Backlog
DEV-US-0177 | EPIC-ACC | EPIC-ACC-F03 | QA: Expense management | High | 6 | 36 | 7 | Backlog
DEV-US-0178 | EPIC-ACC | EPIC-ACC-F04 | Backend: Profit/loss | High | 8 | 48 | 7 | Backlog
DEV-US-0179 | EPIC-ACC | EPIC-ACC-F04 | Frontend: Profit/loss | High | 8 | 48 | 7 | Backlog
DEV-US-0180 | EPIC-ACC | EPIC-ACC-F04 | Database: Profit/loss | High | 8 | 48 | 7 | Backlog
DEV-US-0181 | EPIC-ACC | EPIC-ACC-F04 | QA: Profit/loss | High | 6 | 36 | 7 | Backlog
DEV-US-0182 | EPIC-ACC | EPIC-ACC-F05 | Backend: Financial reconciliation | High | 8 | 48 | 7 | Backlog
DEV-US-0183 | EPIC-ACC | EPIC-ACC-F05 | Frontend: Financial reconciliation | High | 8 | 48 | 7 | Backlog
DEV-US-0184 | EPIC-ACC | EPIC-ACC-F05 | Database: Financial reconciliation | High | 6 | 36 | 7 | Backlog
DEV-US-0185 | EPIC-ACC | EPIC-ACC-F05 | QA: Financial reconciliation | High | 8 | 48 | 7 | Backlog
DEV-US-0186 | EPIC-OCR | EPIC-OCR-F01 | Backend: Native camera/gallery | Medium | 8 | 48 | 8 | Backlog
DEV-US-0187 | EPIC-OCR | EPIC-OCR-F01 | Frontend: Native camera/gallery | Medium | 8 | 48 | 8 | Backlog
DEV-US-0188 | EPIC-OCR | EPIC-OCR-F01 | Database: Native camera/gallery | Medium | 6 | 36 | 8 | Backlog
DEV-US-0189 | EPIC-OCR | EPIC-OCR-F01 | QA: Native camera/gallery | Medium | 6 | 36 | 8 | Backlog
DEV-US-0190 | EPIC-OCR | EPIC-OCR-F01 | DevOps: Native camera/gallery | High | 7 | 42 | 8 | Backlog
DEV-US-0191 | EPIC-OCR | EPIC-OCR-F02 | Backend: Image compression | Medium | 8 | 48 | 8 | Backlog
DEV-US-0192 | EPIC-OCR | EPIC-OCR-F02 | Frontend: Image compression | Medium | 8 | 48 | 8 | Backlog
DEV-US-0193 | EPIC-OCR | EPIC-OCR-F02 | Database: Image compression | Medium | 6 | 36 | 8 | Backlog
DEV-US-0194 | EPIC-OCR | EPIC-OCR-F02 | QA: Image compression | Medium | 6 | 36 | 8 | Backlog
DEV-US-0195 | EPIC-OCR | EPIC-OCR-F02 | DevOps: Image compression | High | 7 | 42 | 8 | Backlog
DEV-US-0196 | EPIC-OCR | EPIC-OCR-F03 | Backend: OCR extraction | Medium | 8 | 48 | 8 | Backlog
DEV-US-0197 | EPIC-OCR | EPIC-OCR-F03 | Frontend: OCR extraction | Medium | 8 | 48 | 8 | Backlog
DEV-US-0198 | EPIC-OCR | EPIC-OCR-F03 | Database: OCR extraction | Medium | 6 | 36 | 8 | Backlog
DEV-US-0199 | EPIC-OCR | EPIC-OCR-F03 | QA: OCR extraction | Medium | 6 | 36 | 8 | Backlog
DEV-US-0200 | EPIC-OCR | EPIC-OCR-F03 | DevOps: OCR extraction | High | 7 | 42 | 8 | Backlog
DEV-US-0201 | EPIC-OCR | EPIC-OCR-F04 | Backend: AI structuring | Medium | 8 | 48 | 8 | Backlog
DEV-US-0202 | EPIC-OCR | EPIC-OCR-F04 | Frontend: AI structuring | Medium | 8 | 48 | 8 | Backlog
DEV-US-0203 | EPIC-OCR | EPIC-OCR-F04 | Database: AI structuring | Medium | 6 | 36 | 8 | Backlog
DEV-US-0204 | EPIC-OCR | EPIC-OCR-F04 | QA: AI structuring | Medium | 6 | 36 | 8 | Backlog
DEV-US-0205 | EPIC-OCR | EPIC-OCR-F04 | DevOps: AI structuring | High | 7 | 42 | 8 | Backlog
DEV-US-0206 | EPIC-OCR | EPIC-OCR-F05 | Backend: Review and save | Medium | 8 | 48 | 8 | Backlog
DEV-US-0207 | EPIC-OCR | EPIC-OCR-F05 | Frontend: Review and save | Medium | 8 | 48 | 8 | Backlog
DEV-US-0208 | EPIC-OCR | EPIC-OCR-F05 | Database: Review and save | Medium | 6 | 36 | 8 | Backlog
DEV-US-0209 | EPIC-OCR | EPIC-OCR-F05 | QA: Review and save | Medium | 6 | 36 | 8 | Backlog
DEV-US-0210 | EPIC-OCR | EPIC-OCR-F05 | DevOps: Review and save | High | 7 | 42 | 8 | Backlog
DEV-US-0211 | EPIC-AI | EPIC-AI-F01 | Backend: Chat UI | Medium | 5 | 30 | 9 | Backlog
DEV-US-0212 | EPIC-AI | EPIC-AI-F01 | Frontend: Chat UI | Medium | 5 | 30 | 9 | Backlog
DEV-US-0213 | EPIC-AI | EPIC-AI-F01 | Database: Chat UI | Medium | 3 | 18 | 9 | Backlog
DEV-US-0214 | EPIC-AI | EPIC-AI-F01 | QA: Chat UI | Medium | 3 | 18 | 9 | Backlog
DEV-US-0215 | EPIC-AI | EPIC-AI-F01 | DevOps: Chat UI | High | 4 | 24 | 9 | Backlog
DEV-US-0216 | EPIC-AI | EPIC-AI-F02 | Backend: Tool calling | Medium | 5 | 30 | 9 | Backlog
DEV-US-0217 | EPIC-AI | EPIC-AI-F02 | Frontend: Tool calling | Medium | 5 | 30 | 9 | Backlog
DEV-US-0218 | EPIC-AI | EPIC-AI-F02 | Database: Tool calling | Medium | 3 | 18 | 9 | Backlog
DEV-US-0219 | EPIC-AI | EPIC-AI-F02 | QA: Tool calling | Medium | 3 | 18 | 9 | Backlog
DEV-US-0220 | EPIC-AI | EPIC-AI-F02 | DevOps: Tool calling | High | 4 | 24 | 9 | Backlog
DEV-US-0221 | EPIC-AI | EPIC-AI-F03 | Backend: AI permissions | Medium | 5 | 30 | 9 | Backlog
DEV-US-0222 | EPIC-AI | EPIC-AI-F03 | Frontend: AI permissions | Medium | 5 | 30 | 9 | Backlog
DEV-US-0223 | EPIC-AI | EPIC-AI-F03 | Database: AI permissions | Medium | 3 | 18 | 9 | Backlog
DEV-US-0224 | EPIC-AI | EPIC-AI-F03 | QA: AI permissions | Medium | 3 | 18 | 9 | Backlog
DEV-US-0225 | EPIC-AI | EPIC-AI-F03 | DevOps: AI permissions | High | 4 | 24 | 9 | Backlog
DEV-US-0226 | EPIC-AI | EPIC-AI-F04 | Backend: Chat history | Medium | 5 | 30 | 9 | Backlog
DEV-US-0227 | EPIC-AI | EPIC-AI-F04 | Frontend: Chat history | Medium | 5 | 30 | 9 | Backlog
DEV-US-0228 | EPIC-AI | EPIC-AI-F04 | Database: Chat history | Medium | 3 | 18 | 9 | Backlog
DEV-US-0229 | EPIC-AI | EPIC-AI-F04 | QA: Chat history | Medium | 3 | 18 | 9 | Backlog
DEV-US-0230 | EPIC-AI | EPIC-AI-F04 | DevOps: Chat history | High | 4 | 24 | 9 | Backlog
DEV-US-0231 | EPIC-AI | EPIC-AI-F05 | Backend: Usage/feedback | Medium | 5 | 30 | 9 | Backlog
DEV-US-0232 | EPIC-AI | EPIC-AI-F05 | Frontend: Usage/feedback | Medium | 5 | 30 | 9 | Backlog
DEV-US-0233 | EPIC-AI | EPIC-AI-F05 | Database: Usage/feedback | Medium | 3 | 18 | 9 | Backlog
DEV-US-0234 | EPIC-AI | EPIC-AI-F05 | QA: Usage/feedback | Medium | 3 | 18 | 9 | Backlog
DEV-US-0235 | EPIC-AI | EPIC-AI-F05 | DevOps: Usage/feedback | High | 4 | 24 | 9 | Backlog
DEV-US-0236 | EPIC-REP | EPIC-REP-F01 | Backend: Milk reports | Medium | 5 | 30 | 10 | Backlog
DEV-US-0237 | EPIC-REP | EPIC-REP-F01 | Frontend: Milk reports | Medium | 5 | 30 | 10 | Backlog
DEV-US-0238 | EPIC-REP | EPIC-REP-F01 | Database: Milk reports | Medium | 3 | 18 | 10 | Backlog
DEV-US-0239 | EPIC-REP | EPIC-REP-F01 | QA: Milk reports | Medium | 3 | 18 | 10 | Backlog
DEV-US-0240 | EPIC-REP | EPIC-REP-F02 | Backend: Financial reports | Medium | 7 | 42 | 10 | Backlog
DEV-US-0241 | EPIC-REP | EPIC-REP-F02 | Frontend: Financial reports | Medium | 5 | 30 | 10 | Backlog
DEV-US-0242 | EPIC-REP | EPIC-REP-F02 | Database: Financial reports | Medium | 3 | 18 | 10 | Backlog
DEV-US-0243 | EPIC-REP | EPIC-REP-F02 | QA: Financial reports | Medium | 3 | 18 | 10 | Backlog
DEV-US-0244 | EPIC-REP | EPIC-REP-F03 | Backend: Animal reports | Medium | 5 | 30 | 10 | Backlog
DEV-US-0245 | EPIC-REP | EPIC-REP-F03 | Frontend: Animal reports | Medium | 7 | 42 | 10 | Backlog
DEV-US-0246 | EPIC-REP | EPIC-REP-F03 | Database: Animal reports | Medium | 3 | 18 | 10 | Backlog
DEV-US-0247 | EPIC-REP | EPIC-REP-F03 | QA: Animal reports | Medium | 3 | 18 | 10 | Backlog
DEV-US-0248 | EPIC-REP | EPIC-REP-F04 | Backend: Export/print | Medium | 5 | 30 | 10 | Backlog
DEV-US-0249 | EPIC-REP | EPIC-REP-F04 | Frontend: Export/print | Medium | 5 | 30 | 10 | Backlog
DEV-US-0250 | EPIC-REP | EPIC-REP-F04 | Database: Export/print | Medium | 5 | 30 | 10 | Backlog
DEV-US-0251 | EPIC-REP | EPIC-REP-F04 | QA: Export/print | Medium | 3 | 18 | 10 | Backlog
DEV-US-0252 | EPIC-REP | EPIC-REP-F05 | Backend: Charts/filters | Medium | 5 | 30 | 10 | Backlog
DEV-US-0253 | EPIC-REP | EPIC-REP-F05 | Frontend: Charts/filters | Medium | 5 | 30 | 10 | Backlog
DEV-US-0254 | EPIC-REP | EPIC-REP-F05 | Database: Charts/filters | Medium | 3 | 18 | 10 | Backlog
DEV-US-0255 | EPIC-REP | EPIC-REP-F05 | QA: Charts/filters | Medium | 5 | 30 | 10 | Backlog
DEV-US-0256 | EPIC-NOTIF | EPIC-NOTIF-F01 | Backend: Inbox | Medium | 5 | 30 | 11 | Backlog
DEV-US-0257 | EPIC-NOTIF | EPIC-NOTIF-F01 | Frontend: Inbox | Medium | 5 | 30 | 11 | Backlog
DEV-US-0258 | EPIC-NOTIF | EPIC-NOTIF-F01 | Database: Inbox | Medium | 3 | 18 | 11 | Backlog
DEV-US-0259 | EPIC-NOTIF | EPIC-NOTIF-F01 | QA: Inbox | Medium | 3 | 18 | 11 | Backlog
DEV-US-0260 | EPIC-NOTIF | EPIC-NOTIF-F01 | DevOps: Inbox | High | 4 | 24 | 11 | Backlog
DEV-US-0261 | EPIC-NOTIF | EPIC-NOTIF-F02 | Backend: Push subscription | Medium | 5 | 30 | 11 | Backlog
DEV-US-0262 | EPIC-NOTIF | EPIC-NOTIF-F02 | Frontend: Push subscription | Medium | 5 | 30 | 11 | Backlog
DEV-US-0263 | EPIC-NOTIF | EPIC-NOTIF-F02 | Database: Push subscription | Medium | 3 | 18 | 11 | Backlog
DEV-US-0264 | EPIC-NOTIF | EPIC-NOTIF-F02 | QA: Push subscription | Medium | 3 | 18 | 11 | Backlog
DEV-US-0265 | EPIC-NOTIF | EPIC-NOTIF-F02 | DevOps: Push subscription | High | 4 | 24 | 11 | Backlog
DEV-US-0266 | EPIC-NOTIF | EPIC-NOTIF-F03 | Backend: Preferences | Medium | 5 | 30 | 11 | Backlog
DEV-US-0267 | EPIC-NOTIF | EPIC-NOTIF-F03 | Frontend: Preferences | Medium | 5 | 30 | 11 | Backlog
DEV-US-0268 | EPIC-NOTIF | EPIC-NOTIF-F03 | Database: Preferences | Medium | 3 | 18 | 11 | Backlog
DEV-US-0269 | EPIC-NOTIF | EPIC-NOTIF-F03 | QA: Preferences | Medium | 3 | 18 | 11 | Backlog
DEV-US-0270 | EPIC-NOTIF | EPIC-NOTIF-F03 | DevOps: Preferences | High | 4 | 24 | 11 | Backlog
DEV-US-0271 | EPIC-NOTIF | EPIC-NOTIF-F04 | Backend: Admin broadcasts | Medium | 5 | 30 | 11 | Backlog
DEV-US-0272 | EPIC-NOTIF | EPIC-NOTIF-F04 | Frontend: Admin broadcasts | Medium | 5 | 30 | 11 | Backlog
DEV-US-0273 | EPIC-NOTIF | EPIC-NOTIF-F04 | Database: Admin broadcasts | Medium | 3 | 18 | 11 | Backlog
DEV-US-0274 | EPIC-NOTIF | EPIC-NOTIF-F04 | QA: Admin broadcasts | Medium | 3 | 18 | 11 | Backlog
DEV-US-0275 | EPIC-NOTIF | EPIC-NOTIF-F04 | DevOps: Admin broadcasts | High | 4 | 24 | 11 | Backlog
DEV-US-0276 | EPIC-NOTIF | EPIC-NOTIF-F05 | Backend: Delivery logs | Medium | 5 | 30 | 11 | Backlog
DEV-US-0277 | EPIC-NOTIF | EPIC-NOTIF-F05 | Frontend: Delivery logs | Medium | 5 | 30 | 11 | Backlog
DEV-US-0278 | EPIC-NOTIF | EPIC-NOTIF-F05 | Database: Delivery logs | Medium | 3 | 18 | 11 | Backlog
DEV-US-0279 | EPIC-NOTIF | EPIC-NOTIF-F05 | QA: Delivery logs | Medium | 3 | 18 | 11 | Backlog
DEV-US-0280 | EPIC-NOTIF | EPIC-NOTIF-F05 | DevOps: Delivery logs | High | 4 | 24 | 11 | Backlog
DEV-US-0281 | EPIC-SET-PROF | EPIC-SET-PROF-F01 | Backend: Profile page | Medium | 5 | 30 | 12 | Backlog
DEV-US-0282 | EPIC-SET-PROF | EPIC-SET-PROF-F01 | Frontend: Profile page | Medium | 5 | 30 | 12 | Backlog
DEV-US-0283 | EPIC-SET-PROF | EPIC-SET-PROF-F01 | Database: Profile page | Medium | 3 | 18 | 12 | Backlog
DEV-US-0284 | EPIC-SET-PROF | EPIC-SET-PROF-F01 | QA: Profile page | Medium | 3 | 18 | 12 | Backlog
DEV-US-0285 | EPIC-SET-PROF | EPIC-SET-PROF-F02 | Backend: Security settings | Medium | 7 | 42 | 12 | Backlog
DEV-US-0286 | EPIC-SET-PROF | EPIC-SET-PROF-F02 | Frontend: Security settings | Medium | 5 | 30 | 12 | Backlog
DEV-US-0287 | EPIC-SET-PROF | EPIC-SET-PROF-F02 | Database: Security settings | Medium | 3 | 18 | 12 | Backlog
DEV-US-0288 | EPIC-SET-PROF | EPIC-SET-PROF-F02 | QA: Security settings | Medium | 3 | 18 | 12 | Backlog
DEV-US-0289 | EPIC-SET-PROF | EPIC-SET-PROF-F03 | Backend: Appearance/language | Medium | 5 | 30 | 12 | Backlog
DEV-US-0290 | EPIC-SET-PROF | EPIC-SET-PROF-F03 | Frontend: Appearance/language | Medium | 7 | 42 | 12 | Backlog
DEV-US-0291 | EPIC-SET-PROF | EPIC-SET-PROF-F03 | Database: Appearance/language | Medium | 3 | 18 | 12 | Backlog
DEV-US-0292 | EPIC-SET-PROF | EPIC-SET-PROF-F03 | QA: Appearance/language | Medium | 3 | 18 | 12 | Backlog
DEV-US-0293 | EPIC-SET-PROF | EPIC-SET-PROF-F04 | Backend: AI/goal/export settings | Medium | 5 | 30 | 12 | Backlog
DEV-US-0294 | EPIC-SET-PROF | EPIC-SET-PROF-F04 | Frontend: AI/goal/export settings | Medium | 5 | 30 | 12 | Backlog
DEV-US-0295 | EPIC-SET-PROF | EPIC-SET-PROF-F04 | Database: AI/goal/export settings | Medium | 5 | 30 | 12 | Backlog
DEV-US-0296 | EPIC-SET-PROF | EPIC-SET-PROF-F04 | QA: AI/goal/export settings | Medium | 3 | 18 | 12 | Backlog
DEV-US-0297 | EPIC-SET-PROF | EPIC-SET-PROF-F05 | Backend: Statistics | Medium | 5 | 30 | 12 | Backlog
DEV-US-0298 | EPIC-SET-PROF | EPIC-SET-PROF-F05 | Frontend: Statistics | Medium | 5 | 30 | 12 | Backlog
DEV-US-0299 | EPIC-SET-PROF | EPIC-SET-PROF-F05 | Database: Statistics | Medium | 3 | 18 | 12 | Backlog
DEV-US-0300 | EPIC-SET-PROF | EPIC-SET-PROF-F05 | QA: Statistics | Medium | 5 | 30 | 12 | Backlog
DEV-US-0301 | EPIC-SUP | EPIC-SUP-F01 | Backend: Help home | Medium | 5 | 30 | 13 | Backlog
DEV-US-0302 | EPIC-SUP | EPIC-SUP-F01 | Frontend: Help home | Medium | 5 | 30 | 13 | Backlog
DEV-US-0303 | EPIC-SUP | EPIC-SUP-F01 | Database: Help home | Medium | 3 | 18 | 13 | Backlog
DEV-US-0304 | EPIC-SUP | EPIC-SUP-F01 | QA: Help home | Medium | 3 | 18 | 13 | Backlog
DEV-US-0305 | EPIC-SUP | EPIC-SUP-F02 | Backend: FAQ/tutorials | Medium | 7 | 42 | 13 | Backlog
DEV-US-0306 | EPIC-SUP | EPIC-SUP-F02 | Frontend: FAQ/tutorials | Medium | 5 | 30 | 13 | Backlog
DEV-US-0307 | EPIC-SUP | EPIC-SUP-F02 | Database: FAQ/tutorials | Medium | 3 | 18 | 13 | Backlog
DEV-US-0308 | EPIC-SUP | EPIC-SUP-F02 | QA: FAQ/tutorials | Medium | 3 | 18 | 13 | Backlog
DEV-US-0309 | EPIC-SUP | EPIC-SUP-F03 | Backend: Ticket creation | Medium | 5 | 30 | 13 | Backlog
DEV-US-0310 | EPIC-SUP | EPIC-SUP-F03 | Frontend: Ticket creation | Medium | 7 | 42 | 13 | Backlog
DEV-US-0311 | EPIC-SUP | EPIC-SUP-F03 | Database: Ticket creation | Medium | 3 | 18 | 13 | Backlog
DEV-US-0312 | EPIC-SUP | EPIC-SUP-F03 | QA: Ticket creation | Medium | 3 | 18 | 13 | Backlog
DEV-US-0313 | EPIC-SUP | EPIC-SUP-F04 | Backend: Ticket replies | Medium | 5 | 30 | 13 | Backlog
DEV-US-0314 | EPIC-SUP | EPIC-SUP-F04 | Frontend: Ticket replies | Medium | 5 | 30 | 13 | Backlog
DEV-US-0315 | EPIC-SUP | EPIC-SUP-F04 | Database: Ticket replies | Medium | 5 | 30 | 13 | Backlog
DEV-US-0316 | EPIC-SUP | EPIC-SUP-F04 | QA: Ticket replies | Medium | 3 | 18 | 13 | Backlog
DEV-US-0317 | EPIC-SUP | EPIC-SUP-F05 | Backend: Support notifications | Medium | 5 | 30 | 13 | Backlog
DEV-US-0318 | EPIC-SUP | EPIC-SUP-F05 | Frontend: Support notifications | Medium | 5 | 30 | 13 | Backlog
DEV-US-0319 | EPIC-SUP | EPIC-SUP-F05 | Database: Support notifications | Medium | 3 | 18 | 13 | Backlog
DEV-US-0320 | EPIC-SUP | EPIC-SUP-F05 | QA: Support notifications | Medium | 5 | 30 | 13 | Backlog
DEV-US-0321 | EPIC-ACH | EPIC-ACH-F01 | Backend: Achievement catalog | Medium | 5 | 30 | 13 | Backlog
DEV-US-0322 | EPIC-ACH | EPIC-ACH-F01 | Frontend: Achievement catalog | Medium | 5 | 30 | 13 | Backlog
DEV-US-0323 | EPIC-ACH | EPIC-ACH-F01 | Database: Achievement catalog | Medium | 3 | 18 | 13 | Backlog
DEV-US-0324 | EPIC-ACH | EPIC-ACH-F01 | QA: Achievement catalog | Medium | 3 | 18 | 13 | Backlog
DEV-US-0325 | EPIC-ACH | EPIC-ACH-F02 | Backend: Score engine | Medium | 7 | 42 | 13 | Backlog
DEV-US-0326 | EPIC-ACH | EPIC-ACH-F02 | Frontend: Score engine | Medium | 5 | 30 | 13 | Backlog
DEV-US-0327 | EPIC-ACH | EPIC-ACH-F02 | Database: Score engine | Medium | 3 | 18 | 13 | Backlog
DEV-US-0328 | EPIC-ACH | EPIC-ACH-F02 | QA: Score engine | Medium | 3 | 18 | 13 | Backlog
DEV-US-0329 | EPIC-ACH | EPIC-ACH-F03 | Backend: Leaderboard | Medium | 5 | 30 | 13 | Backlog
DEV-US-0330 | EPIC-ACH | EPIC-ACH-F03 | Frontend: Leaderboard | Medium | 7 | 42 | 13 | Backlog
DEV-US-0331 | EPIC-ACH | EPIC-ACH-F03 | Database: Leaderboard | Medium | 3 | 18 | 13 | Backlog
DEV-US-0332 | EPIC-ACH | EPIC-ACH-F03 | QA: Leaderboard | Medium | 3 | 18 | 13 | Backlog
DEV-US-0333 | EPIC-ACH | EPIC-ACH-F04 | Backend: Badges | Medium | 5 | 30 | 13 | Backlog
DEV-US-0334 | EPIC-ACH | EPIC-ACH-F04 | Frontend: Badges | Medium | 5 | 30 | 13 | Backlog
DEV-US-0335 | EPIC-ACH | EPIC-ACH-F04 | Database: Badges | Medium | 5 | 30 | 13 | Backlog
DEV-US-0336 | EPIC-ACH | EPIC-ACH-F04 | QA: Badges | Medium | 3 | 18 | 13 | Backlog
DEV-US-0337 | EPIC-ACH | EPIC-ACH-F05 | Backend: Sharing | Medium | 5 | 30 | 13 | Backlog
DEV-US-0338 | EPIC-ACH | EPIC-ACH-F05 | Frontend: Sharing | Medium | 5 | 30 | 13 | Backlog
DEV-US-0339 | EPIC-ACH | EPIC-ACH-F05 | Database: Sharing | Medium | 3 | 18 | 13 | Backlog
DEV-US-0340 | EPIC-ACH | EPIC-ACH-F05 | QA: Sharing | Medium | 5 | 30 | 13 | Backlog
DEV-US-0341 | EPIC-ADMIN | EPIC-ADMIN-F01 | Backend: Admin dashboard | Medium | 8 | 48 | 14 | Backlog
DEV-US-0342 | EPIC-ADMIN | EPIC-ADMIN-F01 | Frontend: Admin dashboard | Medium | 8 | 48 | 14 | Backlog
DEV-US-0343 | EPIC-ADMIN | EPIC-ADMIN-F01 | Database: Admin dashboard | Medium | 6 | 36 | 14 | Backlog
DEV-US-0344 | EPIC-ADMIN | EPIC-ADMIN-F01 | QA: Admin dashboard | Medium | 6 | 36 | 14 | Backlog
DEV-US-0345 | EPIC-ADMIN | EPIC-ADMIN-F01 | DevOps: Admin dashboard | High | 7 | 42 | 14 | Backlog
DEV-US-0346 | EPIC-ADMIN | EPIC-ADMIN-F02 | Backend: Farm details | Medium | 8 | 48 | 14 | Backlog
DEV-US-0347 | EPIC-ADMIN | EPIC-ADMIN-F02 | Frontend: Farm details | Medium | 8 | 48 | 14 | Backlog
DEV-US-0348 | EPIC-ADMIN | EPIC-ADMIN-F02 | Database: Farm details | Medium | 6 | 36 | 14 | Backlog
DEV-US-0349 | EPIC-ADMIN | EPIC-ADMIN-F02 | QA: Farm details | Medium | 6 | 36 | 14 | Backlog
DEV-US-0350 | EPIC-ADMIN | EPIC-ADMIN-F02 | DevOps: Farm details | High | 7 | 42 | 14 | Backlog
DEV-US-0351 | EPIC-ADMIN | EPIC-ADMIN-F03 | Backend: User/farm management | Medium | 8 | 48 | 14 | Backlog
DEV-US-0352 | EPIC-ADMIN | EPIC-ADMIN-F03 | Frontend: User/farm management | Medium | 8 | 48 | 14 | Backlog
DEV-US-0353 | EPIC-ADMIN | EPIC-ADMIN-F03 | Database: User/farm management | Medium | 6 | 36 | 14 | Backlog
DEV-US-0354 | EPIC-ADMIN | EPIC-ADMIN-F03 | QA: User/farm management | Medium | 6 | 36 | 14 | Backlog
DEV-US-0355 | EPIC-ADMIN | EPIC-ADMIN-F03 | DevOps: User/farm management | High | 7 | 42 | 14 | Backlog
DEV-US-0356 | EPIC-ADMIN | EPIC-ADMIN-F04 | Backend: Subscriptions/trials | Medium | 8 | 48 | 14 | Backlog
DEV-US-0357 | EPIC-ADMIN | EPIC-ADMIN-F04 | Frontend: Subscriptions/trials | Medium | 8 | 48 | 14 | Backlog
DEV-US-0358 | EPIC-ADMIN | EPIC-ADMIN-F04 | Database: Subscriptions/trials | Medium | 6 | 36 | 14 | Backlog
DEV-US-0359 | EPIC-ADMIN | EPIC-ADMIN-F04 | QA: Subscriptions/trials | Medium | 6 | 36 | 14 | Backlog
DEV-US-0360 | EPIC-ADMIN | EPIC-ADMIN-F04 | DevOps: Subscriptions/trials | High | 7 | 42 | 14 | Backlog
DEV-US-0361 | EPIC-ADMIN | EPIC-ADMIN-F05 | Backend: Notification center | Medium | 8 | 48 | 14 | Backlog
DEV-US-0362 | EPIC-ADMIN | EPIC-ADMIN-F05 | Frontend: Notification center | Medium | 8 | 48 | 14 | Backlog
DEV-US-0363 | EPIC-ADMIN | EPIC-ADMIN-F05 | Database: Notification center | Medium | 6 | 36 | 14 | Backlog
DEV-US-0364 | EPIC-ADMIN | EPIC-ADMIN-F05 | QA: Notification center | Medium | 6 | 36 | 14 | Backlog
DEV-US-0365 | EPIC-ADMIN | EPIC-ADMIN-F05 | DevOps: Notification center | High | 7 | 42 | 14 | Backlog
DEV-US-0366 | EPIC-SEC | EPIC-SEC-F01 | Backend: RLS validation | High | 8 | 48 | 15 | Backlog
DEV-US-0367 | EPIC-SEC | EPIC-SEC-F01 | Frontend: RLS validation | High | 8 | 48 | 15 | Backlog
DEV-US-0368 | EPIC-SEC | EPIC-SEC-F01 | Database: RLS validation | High | 6 | 36 | 15 | Backlog
DEV-US-0369 | EPIC-SEC | EPIC-SEC-F01 | QA: RLS validation | High | 6 | 36 | 15 | Backlog
DEV-US-0370 | EPIC-SEC | EPIC-SEC-F01 | DevOps: RLS validation | High | 7 | 42 | 15 | Backlog
DEV-US-0371 | EPIC-SEC | EPIC-SEC-F02 | Backend: API hardening | High | 8 | 48 | 15 | Backlog
DEV-US-0372 | EPIC-SEC | EPIC-SEC-F02 | Frontend: API hardening | High | 8 | 48 | 15 | Backlog
DEV-US-0373 | EPIC-SEC | EPIC-SEC-F02 | Database: API hardening | High | 6 | 36 | 15 | Backlog
DEV-US-0374 | EPIC-SEC | EPIC-SEC-F02 | QA: API hardening | High | 6 | 36 | 15 | Backlog
DEV-US-0375 | EPIC-SEC | EPIC-SEC-F02 | DevOps: API hardening | High | 7 | 42 | 15 | Backlog
DEV-US-0376 | EPIC-SEC | EPIC-SEC-F03 | Backend: Storage hardening | High | 8 | 48 | 15 | Backlog
DEV-US-0377 | EPIC-SEC | EPIC-SEC-F03 | Frontend: Storage hardening | High | 8 | 48 | 15 | Backlog
DEV-US-0378 | EPIC-SEC | EPIC-SEC-F03 | Database: Storage hardening | High | 6 | 36 | 15 | Backlog
DEV-US-0379 | EPIC-SEC | EPIC-SEC-F03 | QA: Storage hardening | High | 6 | 36 | 15 | Backlog
DEV-US-0380 | EPIC-SEC | EPIC-SEC-F03 | DevOps: Storage hardening | High | 7 | 42 | 15 | Backlog
DEV-US-0381 | EPIC-SEC | EPIC-SEC-F04 | Backend: AI/OCR security | High | 8 | 48 | 15 | Backlog
DEV-US-0382 | EPIC-SEC | EPIC-SEC-F04 | Frontend: AI/OCR security | High | 8 | 48 | 15 | Backlog
DEV-US-0383 | EPIC-SEC | EPIC-SEC-F04 | Database: AI/OCR security | High | 6 | 36 | 15 | Backlog
DEV-US-0384 | EPIC-SEC | EPIC-SEC-F04 | QA: AI/OCR security | High | 6 | 36 | 15 | Backlog
DEV-US-0385 | EPIC-SEC | EPIC-SEC-F04 | DevOps: AI/OCR security | High | 7 | 42 | 15 | Backlog
DEV-US-0386 | EPIC-SEC | EPIC-SEC-F05 | Backend: Audit/monitoring | High | 8 | 48 | 15 | Backlog
DEV-US-0387 | EPIC-SEC | EPIC-SEC-F05 | Frontend: Audit/monitoring | High | 8 | 48 | 15 | Backlog
DEV-US-0388 | EPIC-SEC | EPIC-SEC-F05 | Database: Audit/monitoring | High | 6 | 36 | 15 | Backlog
DEV-US-0389 | EPIC-SEC | EPIC-SEC-F05 | QA: Audit/monitoring | High | 6 | 36 | 15 | Backlog
DEV-US-0390 | EPIC-SEC | EPIC-SEC-F05 | DevOps: Audit/monitoring | High | 7 | 42 | 15 | Backlog
DEV-US-0391 | EPIC-PERF | EPIC-PERF-F01 | Backend: Home performance | Medium | 5 | 30 | 16 | Backlog
DEV-US-0392 | EPIC-PERF | EPIC-PERF-F01 | Frontend: Home performance | Medium | 5 | 30 | 16 | Backlog
DEV-US-0393 | EPIC-PERF | EPIC-PERF-F01 | Database: Home performance | Medium | 3 | 18 | 16 | Backlog
DEV-US-0394 | EPIC-PERF | EPIC-PERF-F01 | QA: Home performance | Medium | 3 | 18 | 16 | Backlog
DEV-US-0395 | EPIC-PERF | EPIC-PERF-F01 | DevOps: Home performance | High | 4 | 24 | 16 | Backlog
DEV-US-0396 | EPIC-PERF | EPIC-PERF-F02 | Backend: Query optimization | Medium | 5 | 30 | 16 | Backlog
DEV-US-0397 | EPIC-PERF | EPIC-PERF-F02 | Frontend: Query optimization | Medium | 5 | 30 | 16 | Backlog
DEV-US-0398 | EPIC-PERF | EPIC-PERF-F02 | Database: Query optimization | Medium | 3 | 18 | 16 | Backlog
DEV-US-0399 | EPIC-PERF | EPIC-PERF-F02 | QA: Query optimization | Medium | 3 | 18 | 16 | Backlog
DEV-US-0400 | EPIC-PERF | EPIC-PERF-F02 | DevOps: Query optimization | High | 4 | 24 | 16 | Backlog
DEV-US-0401 | EPIC-PERF | EPIC-PERF-F03 | Backend: Report performance | Medium | 5 | 30 | 16 | Backlog
DEV-US-0402 | EPIC-PERF | EPIC-PERF-F03 | Frontend: Report performance | Medium | 5 | 30 | 16 | Backlog
DEV-US-0403 | EPIC-PERF | EPIC-PERF-F03 | Database: Report performance | Medium | 3 | 18 | 16 | Backlog
DEV-US-0404 | EPIC-PERF | EPIC-PERF-F03 | QA: Report performance | Medium | 3 | 18 | 16 | Backlog
DEV-US-0405 | EPIC-PERF | EPIC-PERF-F03 | DevOps: Report performance | High | 4 | 24 | 16 | Backlog
DEV-US-0406 | EPIC-PERF | EPIC-PERF-F04 | Backend: OCR/AI latency | Medium | 5 | 30 | 16 | Backlog
DEV-US-0407 | EPIC-PERF | EPIC-PERF-F04 | Frontend: OCR/AI latency | Medium | 5 | 30 | 16 | Backlog
DEV-US-0408 | EPIC-PERF | EPIC-PERF-F04 | Database: OCR/AI latency | Medium | 3 | 18 | 16 | Backlog
DEV-US-0409 | EPIC-PERF | EPIC-PERF-F04 | QA: OCR/AI latency | Medium | 3 | 18 | 16 | Backlog
DEV-US-0410 | EPIC-PERF | EPIC-PERF-F04 | DevOps: OCR/AI latency | High | 4 | 24 | 16 | Backlog
DEV-US-0411 | EPIC-PERF | EPIC-PERF-F05 | Backend: Bundle optimization | Medium | 5 | 30 | 16 | Backlog
DEV-US-0412 | EPIC-PERF | EPIC-PERF-F05 | Frontend: Bundle optimization | Medium | 5 | 30 | 16 | Backlog
DEV-US-0413 | EPIC-PERF | EPIC-PERF-F05 | Database: Bundle optimization | Medium | 3 | 18 | 16 | Backlog
DEV-US-0414 | EPIC-PERF | EPIC-PERF-F05 | QA: Bundle optimization | Medium | 3 | 18 | 16 | Backlog
DEV-US-0415 | EPIC-PERF | EPIC-PERF-F05 | DevOps: Bundle optimization | High | 4 | 24 | 16 | Backlog
DEV-US-0416 | EPIC-REG | EPIC-REG-F01 | Backend: Regression pack | Medium | 5 | 30 | 17 | Backlog
DEV-US-0417 | EPIC-REG | EPIC-REG-F01 | Frontend: Regression pack | Medium | 5 | 30 | 17 | Backlog
DEV-US-0418 | EPIC-REG | EPIC-REG-F01 | Database: Regression pack | Medium | 3 | 18 | 17 | Backlog
DEV-US-0419 | EPIC-REG | EPIC-REG-F01 | QA: Regression pack | Medium | 3 | 18 | 17 | Backlog
DEV-US-0420 | EPIC-REG | EPIC-REG-F02 | Backend: Defect triage | Medium | 7 | 42 | 17 | Backlog
DEV-US-0421 | EPIC-REG | EPIC-REG-F02 | Frontend: Defect triage | Medium | 5 | 30 | 17 | Backlog
DEV-US-0422 | EPIC-REG | EPIC-REG-F02 | Database: Defect triage | Medium | 3 | 18 | 17 | Backlog
DEV-US-0423 | EPIC-REG | EPIC-REG-F02 | QA: Defect triage | Medium | 3 | 18 | 17 | Backlog
DEV-US-0424 | EPIC-REG | EPIC-REG-F03 | Backend: Financial regression | Medium | 5 | 30 | 17 | Backlog
DEV-US-0425 | EPIC-REG | EPIC-REG-F03 | Frontend: Financial regression | Medium | 7 | 42 | 17 | Backlog
DEV-US-0426 | EPIC-REG | EPIC-REG-F03 | Database: Financial regression | Medium | 3 | 18 | 17 | Backlog
DEV-US-0427 | EPIC-REG | EPIC-REG-F03 | QA: Financial regression | Medium | 3 | 18 | 17 | Backlog
DEV-US-0428 | EPIC-REG | EPIC-REG-F04 | Backend: Mobile regression | Medium | 5 | 30 | 17 | Backlog
DEV-US-0429 | EPIC-REG | EPIC-REG-F04 | Frontend: Mobile regression | Medium | 5 | 30 | 17 | Backlog
DEV-US-0430 | EPIC-REG | EPIC-REG-F04 | Database: Mobile regression | Medium | 5 | 30 | 17 | Backlog
DEV-US-0431 | EPIC-REG | EPIC-REG-F04 | QA: Mobile regression | Medium | 3 | 18 | 17 | Backlog
DEV-US-0432 | EPIC-REG | EPIC-REG-F05 | Backend: Release candidate stabilization | Medium | 5 | 30 | 17 | Backlog
DEV-US-0433 | EPIC-REG | EPIC-REG-F05 | Frontend: Release candidate stabilization | Medium | 5 | 30 | 17 | Backlog
DEV-US-0434 | EPIC-REG | EPIC-REG-F05 | Database: Release candidate stabilization | Medium | 3 | 18 | 17 | Backlog
DEV-US-0435 | EPIC-REG | EPIC-REG-F05 | QA: Release candidate stabilization | Medium | 5 | 30 | 17 | Backlog
DEV-US-0436 | EPIC-UAT | EPIC-UAT-F01 | Backend: UAT environment | Medium | 5 | 30 | 18 | Backlog
DEV-US-0437 | EPIC-UAT | EPIC-UAT-F01 | Frontend: UAT environment | Medium | 5 | 30 | 18 | Backlog
DEV-US-0438 | EPIC-UAT | EPIC-UAT-F01 | Database: UAT environment | Medium | 3 | 18 | 18 | Backlog
DEV-US-0439 | EPIC-UAT | EPIC-UAT-F01 | QA: UAT environment | Medium | 3 | 18 | 18 | Backlog
DEV-US-0440 | EPIC-UAT | EPIC-UAT-F02 | Backend: UAT defect support | Medium | 7 | 42 | 18 | Backlog
DEV-US-0441 | EPIC-UAT | EPIC-UAT-F02 | Frontend: UAT defect support | Medium | 5 | 30 | 18 | Backlog
DEV-US-0442 | EPIC-UAT | EPIC-UAT-F02 | Database: UAT defect support | Medium | 3 | 18 | 18 | Backlog
DEV-US-0443 | EPIC-UAT | EPIC-UAT-F02 | QA: UAT defect support | Medium | 3 | 18 | 18 | Backlog
DEV-US-0444 | EPIC-UAT | EPIC-UAT-F03 | Backend: Training support | Medium | 5 | 30 | 18 | Backlog
DEV-US-0445 | EPIC-UAT | EPIC-UAT-F03 | Frontend: Training support | Medium | 7 | 42 | 18 | Backlog
DEV-US-0446 | EPIC-UAT | EPIC-UAT-F03 | Database: Training support | Medium | 3 | 18 | 18 | Backlog
DEV-US-0447 | EPIC-UAT | EPIC-UAT-F03 | QA: Training support | Medium | 3 | 18 | 18 | Backlog
DEV-US-0448 | EPIC-UAT | EPIC-UAT-F04 | Backend: Pilot readiness | Medium | 5 | 30 | 18 | Backlog
DEV-US-0449 | EPIC-UAT | EPIC-UAT-F04 | Frontend: Pilot readiness | Medium | 5 | 30 | 18 | Backlog
DEV-US-0450 | EPIC-UAT | EPIC-UAT-F04 | Database: Pilot readiness | Medium | 5 | 30 | 18 | Backlog
DEV-US-0451 | EPIC-UAT | EPIC-UAT-F04 | QA: Pilot readiness | Medium | 3 | 18 | 18 | Backlog
DEV-US-0452 | EPIC-UAT | EPIC-UAT-F05 | Backend: Sign-off evidence | Medium | 5 | 30 | 18 | Backlog
DEV-US-0453 | EPIC-UAT | EPIC-UAT-F05 | Frontend: Sign-off evidence | Medium | 5 | 30 | 18 | Backlog
DEV-US-0454 | EPIC-UAT | EPIC-UAT-F05 | Database: Sign-off evidence | Medium | 3 | 18 | 18 | Backlog
DEV-US-0455 | EPIC-UAT | EPIC-UAT-F05 | QA: Sign-off evidence | Medium | 5 | 30 | 18 | Backlog
DEV-US-0456 | EPIC-REL | EPIC-REL-F01 | Backend: Release calendar | High | 5 | 30 | 19 | Backlog
DEV-US-0457 | EPIC-REL | EPIC-REL-F01 | Frontend: Release calendar | High | 5 | 30 | 19 | Backlog
DEV-US-0458 | EPIC-REL | EPIC-REL-F01 | Database: Release calendar | High | 3 | 18 | 19 | Backlog
DEV-US-0459 | EPIC-REL | EPIC-REL-F01 | QA: Release calendar | High | 3 | 18 | 19 | Backlog
DEV-US-0460 | EPIC-REL | EPIC-REL-F01 | DevOps: Release calendar | High | 4 | 24 | 19 | Backlog
DEV-US-0461 | EPIC-REL | EPIC-REL-F02 | Backend: Launch checklist | High | 5 | 30 | 19 | Backlog
DEV-US-0462 | EPIC-REL | EPIC-REL-F02 | Frontend: Launch checklist | High | 5 | 30 | 19 | Backlog
DEV-US-0463 | EPIC-REL | EPIC-REL-F02 | Database: Launch checklist | High | 3 | 18 | 19 | Backlog
DEV-US-0464 | EPIC-REL | EPIC-REL-F02 | QA: Launch checklist | High | 3 | 18 | 19 | Backlog
DEV-US-0465 | EPIC-REL | EPIC-REL-F02 | DevOps: Launch checklist | High | 4 | 24 | 19 | Backlog
DEV-US-0466 | EPIC-REL | EPIC-REL-F03 | Backend: Migration runbook | High | 5 | 30 | 19 | Backlog
DEV-US-0467 | EPIC-REL | EPIC-REL-F03 | Frontend: Migration runbook | High | 5 | 30 | 19 | Backlog
DEV-US-0468 | EPIC-REL | EPIC-REL-F03 | Database: Migration runbook | High | 3 | 18 | 19 | Backlog
DEV-US-0469 | EPIC-REL | EPIC-REL-F03 | QA: Migration runbook | High | 3 | 18 | 19 | Backlog
DEV-US-0470 | EPIC-REL | EPIC-REL-F03 | DevOps: Migration runbook | High | 4 | 24 | 19 | Backlog
DEV-US-0471 | EPIC-REL | EPIC-REL-F04 | Backend: Rollback plan | High | 5 | 30 | 19 | Backlog
DEV-US-0472 | EPIC-REL | EPIC-REL-F04 | Frontend: Rollback plan | High | 5 | 30 | 19 | Backlog
DEV-US-0473 | EPIC-REL | EPIC-REL-F04 | Database: Rollback plan | High | 3 | 18 | 19 | Backlog
DEV-US-0474 | EPIC-REL | EPIC-REL-F04 | QA: Rollback plan | High | 3 | 18 | 19 | Backlog
DEV-US-0475 | EPIC-REL | EPIC-REL-F04 | DevOps: Rollback plan | High | 4 | 24 | 19 | Backlog
DEV-US-0476 | EPIC-REL | EPIC-REL-F05 | Backend: Hypercare | High | 5 | 30 | 19 | Backlog
DEV-US-0477 | EPIC-REL | EPIC-REL-F05 | Frontend: Hypercare | High | 5 | 30 | 19 | Backlog
DEV-US-0478 | EPIC-REL | EPIC-REL-F05 | Database: Hypercare | High | 3 | 18 | 19 | Backlog
DEV-US-0479 | EPIC-REL | EPIC-REL-F05 | QA: Hypercare | High | 3 | 18 | 19 | Backlog
DEV-US-0480 | EPIC-REL | EPIC-REL-F05 | DevOps: Hypercare | High | 4 | 24 | 19 | Backlog