## UAT Scenarios
uatId | scenario | actor | objective | preconditions | steps | expectedOutcome | acceptanceCriteria | status
UAT-001 | Register New Farmer | Farmer | New user selects language, signs up and reaches dashboard. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-002 | Create Farm | Farm Owner | Owner creates/updates farm profile with village/taluka data. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-003 | Add Cow | Farmer | Farmer adds cow and verifies profile/reminders. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-004 | Record Milk | Farmer | Farmer records morning/evening milk and sees dashboard/report impact. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-005 | Complete Vaccination | Farmer/Veterinarian | User records vaccination and completes due reminder. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-006 | Upload Dairy Slip | Farmer | User scans daily/settlement slip, reviews and saves. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-007 | View Settlement | Farm Owner | Owner views settlement, deductions and financial reconciliation. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-008 | Generate Reports | Farm Owner | Owner filters, exports and prints reports. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-009 | Set Goals | Farm Owner | Owner creates goals and tracks progress. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-010 | Use AI Assistant | Farmer | User asks dairy question and validates real-data answer. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-011 | Create Support Ticket | Farmer | User creates ticket with attachment and gets reply. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-012 | Backup and Restore | Farm Owner | Owner creates backup and validates restore workflow. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run
UAT-013 | Admin Analytics Review | Admin | Admin reviews farm details, analytics and protected actions. | User role, farm data and language preference are available. | 1. Start from login. 2. Complete business workflow. 3. Verify UI, database, report, notification and audit outcomes. 4. Repeat language-critical parts. | Workflow completes without support intervention and all data is accurate, localized and traceable. | Business user signs off; no Critical/High defect remains; screenshots/evidence attached. | Not Run