## Security Risks
riskId | risk | rating | description | mitigation | residualRisk | owner | status
SR-001 | Cross-farm data leakage | Critical | RLS/API authorization gap exposes farm data. | RLS tests, farm_id enforcement, admin audit. | Low | Security/Engineering | Open
SR-002 | Financial tampering | Critical | Unauthorized update changes income/profit. | RBAC, transaction RPCs, audit, reconciliation. | Low | Security/Engineering | Open
SR-003 | OCR malicious file | High | Uploaded file abuses parser/storage. | MIME validation, size limits, private bucket, malware scan readiness. | Medium | Security/Engineering | Open
SR-004 | AI prompt injection | High | User input attempts unauthorized tool/data access. | Tool allowlist, permission checks, no raw SQL, output filtering. | Medium | Security/Engineering | Open
SR-005 | Service key exposure | Critical | Service role/OpenAI/OCR keys exposed to client or logs. | Server-only env vars, secret scanning, rotation. | Low | Security/Engineering | Open
SR-006 | Weak PIN/password attack | High | Brute force or reused credentials. | Password policy, PIN lockout, rate limiting, audit. | Medium | Security/Engineering | Open
SR-007 | Admin misuse | High | Privileged action suspends/deletes wrong farm. | Confirmation, reason, protected action logs, least privilege. | Medium | Security/Engineering | Open
SR-008 | Backup exposure | Critical | Backup file leaks complete farm data. | Private bucket, signed URLs, encryption, access audit. | Low | Security/Engineering | Open
SR-009 | Push payload privacy | Medium | Sensitive data appears in OS notification panel. | Payload minimization and user preferences. | Low | Security/Engineering | Open
SR-010 | Report URL leakage | High | Generated report accessible publicly. | Signed URLs, expiry, RLS metadata check. | Low | Security/Engineering | Open
SR-011 | Dependency vulnerability | High | Package vulnerability exploited. | SCA, patch SLAs, CI checks. | Medium | Security/Engineering | Open
SR-012 | Session persistence issue | Medium | Lost/invalid session causes broken navigation. | Session validation, graceful login redirect, device QA. | Low | Security/Engineering | Open
SR-013 | Storage bucket misconfiguration | Critical | OCR slips, reports or backups become publicly readable. | Private-by-default buckets, CI policy checks, signed URL tests. | Low | Security/Engineering | Open
SR-014 | RLS bypass through service API | Critical | Server API using service role omits explicit farm authorization. | Central auth guard, farm access assertion, code review checklist. | Low | Security/Engineering | Open
SR-015 | Sensitive error disclosure | Medium | Stack traces or provider errors reveal internals to user. | Safe error mapping, server-only logs, localized generic messages. | Low | Security/Engineering | Open
SR-016 | Admin notification abuse | Medium | Broadcast sends sensitive or misleading content to wrong farms. | Audience preview, send confirmation, delivery audit and RBAC. | Low | Security/Engineering | Open
SR-017 | Support attachment data leak | High | Ticket attachments are exposed across farms/users. | Ticket-scoped private storage and signed URL authorization. | Low | Security/Engineering | Open
SR-018 | Localization fallback leak | Low | Fallback messages expose technical details in English/Marathi. | Central i18n error catalog and QA language sweep. | Low | Security/Engineering | Open
SR-019 | Offline data conflict | Medium | Queued offline writes overwrite newer financial/animal records. | Conflict detection, server timestamps and user confirmation. | Medium | Security/Engineering | Open
SR-020 | Realtime channel leakage | High | Supabase realtime sends farm notifications to unauthorized clients. | Channel authorization and farm-scoped subscriptions. | Low | Security/Engineering | Open

## AI Risks
riskId | risk | rating | description | mitigation
AI-001 | Hallucinated farm data | High | AI answers fake values. | Use tool-only database retrieval; cite period/source in answer.
AI-002 | Unauthorized data use | Critical | AI uses milk/slip/animal data without permission. | Server-side AI permission checks before tool execution.
AI-003 | Prompt injection | High | User asks model to bypass policy/tool limits. | Instruction hierarchy, tool allowlist, schema validation.
AI-004 | Sensitive data in logs | Medium | AI logs retain private data too long. | Retention policy, deletion, redaction and access limits.
AI-005 | Token/cost abuse | Medium | Excessive AI usage increases cost. | Rate limits, quotas, short context and monitoring.

## STRIDE Threats
threatId | stride | threatDescription | affectedComponents | likelihood | impact | riskRating | mitigation | residualRisk
TH-001 | Spoofing | Spoofing threat against authentication could compromise tenant data, trust or availability. | Authentication | Low | Critical | High | Strong authentication, token validation, session expiry and device/session audit. | Low
TH-002 | Tampering | Tampering threat against authentication could compromise tenant data, trust or availability. | Authentication | Medium | Critical | Critical | Input validation, RLS, transaction integrity, audit logs and protected actions. | Medium
TH-003 | Repudiation | Repudiation threat against authentication could compromise tenant data, trust or availability. | Authentication | Low | Critical | High | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. | Low
TH-004 | Information Disclosure | Information Disclosure threat against authentication could compromise tenant data, trust or availability. | Authentication | Medium | Critical | Critical | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. | Medium
TH-005 | Denial of Service | Denial of Service threat against authentication could compromise tenant data, trust or availability. | Authentication | Medium | Critical | Critical | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. | Medium
TH-006 | Elevation of Privilege | Elevation of Privilege threat against authentication could compromise tenant data, trust or availability. | Authentication | Low | Critical | High | RBAC, role hierarchy, server-side checks, admin confirmation and audit. | Low
TH-007 | Spoofing | Spoofing threat against dashboard could compromise tenant data, trust or availability. | Dashboard | Low | Medium | Medium | Strong authentication, token validation, session expiry and device/session audit. | Low
TH-008 | Tampering | Tampering threat against dashboard could compromise tenant data, trust or availability. | Dashboard | Medium | Medium | Medium | Input validation, RLS, transaction integrity, audit logs and protected actions. | Low
TH-009 | Repudiation | Repudiation threat against dashboard could compromise tenant data, trust or availability. | Dashboard | Low | Medium | Medium | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. | Low
TH-010 | Information Disclosure | Information Disclosure threat against dashboard could compromise tenant data, trust or availability. | Dashboard | Medium | Medium | Medium | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. | Low
TH-011 | Denial of Service | Denial of Service threat against dashboard could compromise tenant data, trust or availability. | Dashboard | Medium | Medium | Medium | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. | Low
TH-012 | Elevation of Privilege | Elevation of Privilege threat against dashboard could compromise tenant data, trust or availability. | Dashboard | Low | Medium | Medium | RBAC, role hierarchy, server-side checks, admin confirmation and audit. | Low
TH-013 | Spoofing | Spoofing threat against cow management could compromise tenant data, trust or availability. | Cow Management | Low | Medium | Medium | Strong authentication, token validation, session expiry and device/session audit. | Low
TH-014 | Tampering | Tampering threat against cow management could compromise tenant data, trust or availability. | Cow Management | Medium | Medium | Medium | Input validation, RLS, transaction integrity, audit logs and protected actions. | Low
TH-015 | Repudiation | Repudiation threat against cow management could compromise tenant data, trust or availability. | Cow Management | Low | Medium | Medium | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. | Low
TH-016 | Information Disclosure | Information Disclosure threat against cow management could compromise tenant data, trust or availability. | Cow Management | Medium | Medium | Medium | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. | Low
TH-017 | Denial of Service | Denial of Service threat against cow management could compromise tenant data, trust or availability. | Cow Management | Medium | Medium | Medium | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. | Low
TH-018 | Elevation of Privilege | Elevation of Privilege threat against cow management could compromise tenant data, trust or availability. | Cow Management | Low | Medium | Medium | RBAC, role hierarchy, server-side checks, admin confirmation and audit. | Low
TH-019 | Spoofing | Spoofing threat against accounting could compromise tenant data, trust or availability. | Accounting | Low | Critical | High | Strong authentication, token validation, session expiry and device/session audit. Financial saves are transactional and reconciled. | Low
TH-020 | Tampering | Tampering threat against accounting could compromise tenant data, trust or availability. | Accounting | Medium | Critical | Critical | Input validation, RLS, transaction integrity, audit logs and protected actions. Financial saves are transactional and reconciled. | Medium
TH-021 | Repudiation | Repudiation threat against accounting could compromise tenant data, trust or availability. | Accounting | Low | Critical | High | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. Financial saves are transactional and reconciled. | Low
TH-022 | Information Disclosure | Information Disclosure threat against accounting could compromise tenant data, trust or availability. | Accounting | Medium | Critical | Critical | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. Financial saves are transactional and reconciled. | Medium
TH-023 | Denial of Service | Denial of Service threat against accounting could compromise tenant data, trust or availability. | Accounting | Medium | Critical | Critical | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. Financial saves are transactional and reconciled. | Medium
TH-024 | Elevation of Privilege | Elevation of Privilege threat against accounting could compromise tenant data, trust or availability. | Accounting | Low | Critical | High | RBAC, role hierarchy, server-side checks, admin confirmation and audit. Financial saves are transactional and reconciled. | Low
TH-025 | Spoofing | Spoofing threat against ocr uploads could compromise tenant data, trust or availability. | OCR Uploads | Low | High | High | Strong authentication, token validation, session expiry and device/session audit. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-026 | Tampering | Tampering threat against ocr uploads could compromise tenant data, trust or availability. | OCR Uploads | Medium | High | High | Input validation, RLS, transaction integrity, audit logs and protected actions. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-027 | Repudiation | Repudiation threat against ocr uploads could compromise tenant data, trust or availability. | OCR Uploads | Low | High | High | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-028 | Information Disclosure | Information Disclosure threat against ocr uploads could compromise tenant data, trust or availability. | OCR Uploads | Medium | High | High | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-029 | Denial of Service | Denial of Service threat against ocr uploads could compromise tenant data, trust or availability. | OCR Uploads | Medium | High | High | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-030 | Elevation of Privilege | Elevation of Privilege threat against ocr uploads could compromise tenant data, trust or availability. | OCR Uploads | Low | High | High | RBAC, role hierarchy, server-side checks, admin confirmation and audit. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-031 | Spoofing | Spoofing threat against ai assistant could compromise tenant data, trust or availability. | AI Assistant | Low | High | High | Strong authentication, token validation, session expiry and device/session audit. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-032 | Tampering | Tampering threat against ai assistant could compromise tenant data, trust or availability. | AI Assistant | Medium | High | High | Input validation, RLS, transaction integrity, audit logs and protected actions. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-033 | Repudiation | Repudiation threat against ai assistant could compromise tenant data, trust or availability. | AI Assistant | Low | High | High | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-034 | Information Disclosure | Information Disclosure threat against ai assistant could compromise tenant data, trust or availability. | AI Assistant | Medium | High | High | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-035 | Denial of Service | Denial of Service threat against ai assistant could compromise tenant data, trust or availability. | AI Assistant | Medium | High | High | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-036 | Elevation of Privilege | Elevation of Privilege threat against ai assistant could compromise tenant data, trust or availability. | AI Assistant | Low | High | High | RBAC, role hierarchy, server-side checks, admin confirmation and audit. Provider keys are server-only; user review is mandatory for financial outputs. | Low
TH-037 | Spoofing | Spoofing threat against reports could compromise tenant data, trust or availability. | Reports | Low | Medium | Medium | Strong authentication, token validation, session expiry and device/session audit. | Low
TH-038 | Tampering | Tampering threat against reports could compromise tenant data, trust or availability. | Reports | Medium | Medium | Medium | Input validation, RLS, transaction integrity, audit logs and protected actions. | Low
TH-039 | Repudiation | Repudiation threat against reports could compromise tenant data, trust or availability. | Reports | Low | Medium | Medium | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. | Low
TH-040 | Information Disclosure | Information Disclosure threat against reports could compromise tenant data, trust or availability. | Reports | Medium | Medium | Medium | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. | Low
TH-041 | Denial of Service | Denial of Service threat against reports could compromise tenant data, trust or availability. | Reports | Medium | Medium | Medium | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. | Low
TH-042 | Elevation of Privilege | Elevation of Privilege threat against reports could compromise tenant data, trust or availability. | Reports | Low | Medium | Medium | RBAC, role hierarchy, server-side checks, admin confirmation and audit. | Low
TH-043 | Spoofing | Spoofing threat against admin panel could compromise tenant data, trust or availability. | Admin Panel | Low | Critical | High | Strong authentication, token validation, session expiry and device/session audit. | Low
TH-044 | Tampering | Tampering threat against admin panel could compromise tenant data, trust or availability. | Admin Panel | Medium | Critical | Critical | Input validation, RLS, transaction integrity, audit logs and protected actions. | Medium
TH-045 | Repudiation | Repudiation threat against admin panel could compromise tenant data, trust or availability. | Admin Panel | Low | Critical | High | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. | Low
TH-046 | Information Disclosure | Information Disclosure threat against admin panel could compromise tenant data, trust or availability. | Admin Panel | Medium | Critical | Critical | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. | Medium
TH-047 | Denial of Service | Denial of Service threat against admin panel could compromise tenant data, trust or availability. | Admin Panel | Medium | Critical | Critical | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. | Medium
TH-048 | Elevation of Privilege | Elevation of Privilege threat against admin panel could compromise tenant data, trust or availability. | Admin Panel | Low | Critical | High | RBAC, role hierarchy, server-side checks, admin confirmation and audit. | Low
TH-049 | Spoofing | Spoofing threat against apis could compromise tenant data, trust or availability. | APIs | Low | High | High | Strong authentication, token validation, session expiry and device/session audit. | Low
TH-050 | Tampering | Tampering threat against apis could compromise tenant data, trust or availability. | APIs | Medium | High | High | Input validation, RLS, transaction integrity, audit logs and protected actions. | Low
TH-051 | Repudiation | Repudiation threat against apis could compromise tenant data, trust or availability. | APIs | Low | High | High | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. | Low
TH-052 | Information Disclosure | Information Disclosure threat against apis could compromise tenant data, trust or availability. | APIs | Medium | High | High | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. | Low
TH-053 | Denial of Service | Denial of Service threat against apis could compromise tenant data, trust or availability. | APIs | Medium | High | High | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. | Low
TH-054 | Elevation of Privilege | Elevation of Privilege threat against apis could compromise tenant data, trust or availability. | APIs | Low | High | High | RBAC, role hierarchy, server-side checks, admin confirmation and audit. | Low
TH-055 | Spoofing | Spoofing threat against storage could compromise tenant data, trust or availability. | Storage | Low | High | High | Strong authentication, token validation, session expiry and device/session audit. | Low
TH-056 | Tampering | Tampering threat against storage could compromise tenant data, trust or availability. | Storage | Medium | High | High | Input validation, RLS, transaction integrity, audit logs and protected actions. | Low
TH-057 | Repudiation | Repudiation threat against storage could compromise tenant data, trust or availability. | Storage | Low | High | High | Immutable audit logs with actor, timestamp, IP/device and before/after metadata. | Low
TH-058 | Information Disclosure | Information Disclosure threat against storage could compromise tenant data, trust or availability. | Storage | Medium | High | High | Farm-scoped RLS, private storage, least privilege, redaction and signed URLs. | Low
TH-059 | Denial of Service | Denial of Service threat against storage could compromise tenant data, trust or availability. | Storage | Medium | High | High | Rate limits, pagination, async jobs, quotas, provider timeout and monitoring. | Low
TH-060 | Elevation of Privilege | Elevation of Privilege threat against storage could compromise tenant data, trust or availability. | Storage | Low | High | High | RBAC, role hierarchy, server-side checks, admin confirmation and audit. | Low