## Training Plan
audience | topics | method | duration | materials | completionCriteria | owner | status
Farmers | Mobile app basics, cow/calf, milk records, reminders, slip upload | Live demo + Marathi quick guide | 2 hours | User guide, screenshots, short videos, FAQ, support scripts | Participant completes assigned UAT/training checklist without assistance. | Product / Support | Planned
Farm Owners | Accounting, settlement, reports, goals, backup | Workshop + reconciliation examples | 3 hours | User guide, screenshots, short videos, FAQ, support scripts | Participant completes assigned UAT/training checklist without assistance. | Product / Support | Planned
Veterinarians | Assigned farms, health records, vaccination/reminder workflows | Role-based walkthrough | 90 minutes | User guide, screenshots, short videos, FAQ, support scripts | Participant completes assigned UAT/training checklist without assistance. | Product / Support | Planned
Administrators | Admin dashboard, farm details, subscriptions, notifications, support | Admin playbook + sandbox | 4 hours | User guide, screenshots, short videos, FAQ, support scripts | Participant completes assigned UAT/training checklist without assistance. | Product / Support | Planned
Support Team | Ticket handling, diagnostics, user guidance, escalation | Support SOP + role play | 4 hours | User guide, screenshots, short videos, FAQ, support scripts | Participant completes assigned UAT/training checklist without assistance. | Product / Support | Planned

## Adoption Plan
Period | Focus
Week 1 | Hands-on onboarding, daily check-ins, slip scanning support
Week 2-4 | Reports/accounting training, reminder discipline, support feedback
30 Days | Usage review, defect review, training refresh
60 Days | Pilot expansion and advanced features
90 Days | Production expansion readiness